| Mechanical |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | DOCUMENT NO: GCS-GEN-001 General Scope of Work | 7.9.2 |  | Minimum 10% of the items or one number, whichever is maximum will be considered as commissioning spares. |  | Please Provide the commission spare part list for all equipment like Annexure D of DOCUMENT NO: GCS-PRS-005 Specification of Gas Compressor Package Sheet 31 of 41 and Sheet 32 of 41 are given like same is to be provided for other equipments to bid clarity and bid competency. | Successful bidder shall prepare the list of commissioning spares based on OEM’s recommendation. OIL/OIL’s consultant shall review the list prior to order of the specific equipments. |
|  |  | DOCUMENT NO: GCS-GEN-001 General Scope of Work | 7.9.3 |  | Apart from above LSTK Contractor shall submit item wise list of recommended spares for 2 years’ smooth operation along with the offer. Prices for the same shall remain valid till the currency of the job. OIL shall place order for the same separately. |  | The same price will not consider for price bid evaluation, kindly confirm. | Price of recommended spares shall not be considered for evaluation of price of the bid. |
|  |  | DOCUMENT NO: GCS-PRS-001 Process Scope of Work |  |  | GAS COMPRESSOR SHED: The shed to be designed to maintain the noise level at outside at 55db, acoustic insulation material shall be provided for sound mitigation. |  | Please provide the acoustic insulation material specification to maintain the noise level below 55db. | The acoustic insulation material selection is in the scope of the EPC/LSTK contractor. The material should be globally used for the same purpose with industrial acceptability in the same environment. OIL/OIL’s consultant shall review the documents. |
|  |  | DOCUMENT NO: GCS-PRS-005 Specification of Gas Compressor Package | 5.2.1 Reciprocating Compressor Package Design |  | In addition to this, the valve dynamic response study shall be carried out. Noise levels of compressor assembly together with drive unit shall not exceed 105 dB(A) at 1-meter distance from the equipment. |  | Compressor manufacturers agree for sound level of 115 dBA for diesel engine driven compressor sets and 105 dBA for motor driven pump sets. Diesel engine being reciprocating machine developing quite high power, sound level is also higher. To achieve sound level of 105 dBA for diesel engine driven compressor set, will have to be provided with acoustic hood which not only increase cost but necessitates larger size Compressor house also increases cost of construction of compressor shed. We look for OIL’s confirmation on acceptance of sound level of 115 dBA for diesel engine driven Compressor sets | The diesel driven compressor engine is not mentioned anywhere for the compressor package prime mover. Please go carefully through the detail specification of the tender. |
|  |  | DOCUMENT NO: GCS-MEC-001 Mechanical Design Basis | iv. Design Considerations for various equipments 1. Pumps: |  | For centrifugal pumps, dual mechanical seal (tandem arrangement) with appropriate seal flush plan shall be provided for hydrocarbon service. Tandem seals shall also be fitted to all pumps, pumping the fluids that are above their flash points. For multistage centrifugal pumps, torsional and lateral critical analysis is to be performed and submitted to OIL for review. |  | For water pump dual seal is not required as such the same is not critical (process) application. This pump can be run on single seal. Kindly confirm. | Please follow the tender specification. |
|  |  | DOCUMENT NO: GCS-MEC-005, Construction of GCS at Makum, Specification for Air Compressor | VOL-II TECHNICAL PART-1 (n) INSTRUMENT / Plant AIR SYSTEM Clause No 3.7, Air Receiver – 3.7.2 |  | Instrument air receiver of five cubic meters’ capacity (minimum) / back up of 30 minutes whichever is more shall be provided. Minimum 3000 Litre IR Air Receiver with auto drains facility. One to be placed after compressor and other to be placed after dryer. 3000 Litre IR Air Receiver (3M*3) – Considering 1cfm/control loop of air consumption for at least one-hour backup in case of complete power failure. |  | Please clarify what would be the capacity of receiver to be supplied and installed after the dryer whether it is 3m3 OR 5m3. Also the backup up written are 1 hr and 30 mins, please clarify. | Bidder to design vessel size for 30 minutes backup to run the entire installation. |
|  |  | DOCUMENT NO: GCS-MEC-005, Construction of GCS at Makum, Specification for Air Compressor | Clause No 3.7, Air Receiver – 3.7.2 |  | All the interconnected piping in compressor, dryer and in-between compressor & dryer, between compressor and vessel (3000L), between dryer and vessel (3000L) should be factory fitted and preferably should be skid mounted. |  | We understand that the 2 compressors along with 2 Nos. Air Receiver, 2 Nos. dryers along with inter-connection pipelines & Filters to be Skid Mounted. Kindly clarify. | Yes |
|  |  | VOL-I Cost Break up Annexure A1 | B.1 Process B.1.6 Nitrogen purging system GCS-PRS-001 Process Scope of work |  | B.1.6 Nitrogen purging system |  | As per the Annexure A1 Nitrogen purging system is to be given. But the same is not mentioned in GCS-PRS-001 Process scope of work. Please clarify if the same is to be supplied. If Yes, Bidder shall need design basis / technical specifications / datasheet to design the system. | Refer to clause (M) Process Utilities and Others…. a) Inert gas system. |
| Instrumentation |  |  |  |  |  |  |  |  |
|  | General |  | General |  | General |  | Bidder request to provide Preliminary Piping & Instrumentation Diagram of the proposed system. | P&ID to be prepared by bidder as part of FEED/detail engineering. Since the project scope comprises of individual OEM packages, so P&ID of these packages will be vendor specific and guidelines given under tender specifications for these packages and instrumentation design basis and scope of work to be followed. For common and interconnecting spaces, the Instrumentation will mostly consist of flow meters, pressure measurement, shutdown valves/MOV, etc. |
|  | VOL. II, Technical Part 9-13, DOCUMENT NO: GCS-INS-FS-311 to 323 |  | Datasheets for field Instruments & Control Valves |  | Quote from tender “Specification for Instruments…” |  | Bidder request to provide process datasheets for Instruments & Control Valves, etc for selection & sizing. | Functional specifications provided for all these items in the tender. Data sheet to be prepared by bidder and quantity to be estimated by bidder as project scope comprises of individual OEM packages, so P&ID of these packages will be vendor specific and guidelines given under tender specifications for these packages and instrumentation design baisis and scope of work to be followed. please note that since the preparation of P&ID are in bidder scope as per specific OEM package, so the type of instruments required can vary but the package should meet the tender specification and all instruments that will be specified after HAZOP & SIL study to be incorporated by bidder. |
|  | VOL. II, Technical Part 5, |  | Cl. No. 4.0, PAGE NO 514 OF 1160 |  | Quote from tender “CONTRACTOR’S SCOPE OF SUPPLY AND INSTALLATION (TABLE – 2)” |  | Bidder request to provide distance between the New Compressor Shed to New Control Room. | Bidder to prepare plot plan and estimate the distance as part of FEED/detail engineering. |
|  | VOL. II, Technical Part 6, DOCUMENT NO: GCS-INS-003 |  | Cl. No. 1.6, Sheet 12 of 22 |  | Quote from tender “MODULE SHUTDOWN AND SAFETY INTEGRITY LEVEL REQUIREMENT.” |  | Bidder understands that PLC controller is separate for process & shutdown. SIL-3 requirement as envisaged is for shutdown application only. Process PLC system & Process field instruments shall be non-SIL. M/s OIL to clarify. | - SIL study will only determine the requirement of SIL3 PLC or not. For process & shutdown of individual compressor package will have own PLC and rest all process to be connected to DCS in control room and shutdown in common PLC at control room. - All gas compressor units should have independent PLC at site and all other packages can be connected to a common PLC system in control room including ESD & F&G. The individual gas compressor PLC should communicate with main DCS in control room. The common PLC in control room should also communicate with DCS. |
|  | VOL. II, Technical Part 6, DOCUMENT NO: GCS-INS-003 |  | Cl. No. 2.0, PAGE NO 636 OF 1160 |  | Quote from tender “Microprocessor based Programmable Controller.” |  | Bidder understands that no redundancy is required at I-O level, Controller level, communication level & Power supply level. M/s OIL to clarify. | Required as per the Instrumentation design basis document and scope of work in the tender. |
|  | VOL. II, Technical Part 5, |  | Cl. No. 2.4.1, PAGE NO 513 OF 1160. Sr. No. J |  | Quote from tender “Supply of start-up and commissioning spares for all instruments and spares for Six years comprehensive AMC as per details.” |  | Bidder request to provide Mandatory & Commissioning spares list for Instrumentation. | Bidder to estimate as a part of AMC quote. Mandatory spares and all other types of spares to be provided for all instrumentation items as pet tender scope defined under " Spares" clause. |
| ELECTRICAL |  |  |  |  |  |  |  |  |
|  |  | Doc No: -GCS-ELE-001 | General |  | General |  | Bidder request to Provide Spare Components list | In the bidder’s scope, OIL/ OIL’s consultant shall verify the documents. |
|  |  | Doc No: -GCS-ELE-001 | General |  | General |  | Bidder request to provide the Overall Layout drawing, for estimating the length of cables & tray. | In the bidder’s scope, OIL/ OIL’s consultant shall verify the documents. |
|  |  | Doc No: -GCS-ELE-001 | (23.1 & 23.5 (d) ) & Sheet no:-35/36 of 51, Page no:-292 of 1160. |  | Earthing & Lightning Protection. |  | In clause 23.1 it states that Earthing Electrode shall be GI pipe but in Clause 23.5 (d) it states that it shall be of copper. Bidder request to clarify it, which shall be considered. | Please consider copper bonded low carbon steel or chemical filled earth electrode and NOT GI pipe electrode. |
|  |  | Doc No: -GCS-ELE-001 | (25.6 & 25.7) & Sheet no: -45 of 51 & Page no; -302 of 1160. |  | Street Lighting & High Masts Lighting |  | Bidder request to specify the height of Street light pole & High masts lighting pole. | Bidder to design the lighting system and calculate pole heights for street lights as well as high mast systems as per design [Para 25.5 (d) and 25.10 of Elect. Design Basis]. |