| Commercial |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 |  | Volume-1 | Commercial | Clause 17.0 | Liquidated damages | It is requested that the maximum capping of the LD may be kept at 5 % instead of 7.5 % presently | Bidder’s request is not acceptable. To be guided by Clause 17.0 of Part-3, Section-I of GCC. |
| 2 |  | Volume-1 | Commercial | Clause 17.0 | Liquidated damages | It is requested that the LD amount may be applied on the value of contract less taxes. | LD will be applicable on the total contract cost which is inclusive of all taxes/duties but exclusive of Service Tax. |
| 3 |  | Volume-1 | Commercial | Clause 17.0 | Liquidated damages | Bidder request for the addition of this clause “However if the Contactor has completed certain part of the work within the scheduled Completion Mechanical completion date and the said part is ready for use and is accepted by OIL, then in that event the LD shall be leviable only on the balance portion of the Contract Value remaining incomplete which shall be reduced in proportion to the completed works which the value of such completed portion bears to the entire value of the works “. | This Project being a complete package, part completion is not acceptable for the purpose of LD. Hence, question of addition of this new clause does not arise. |
| 4 |  | Volume-1 | Commercial | Clause 7.0 page 55/138 |  | In case the work gets extended beyond 24 months for reasons not attributable to Contractor, then the price shall be suitably discussed to accommodate the escalation beyond the said period of 24 months from NOA. | No. Bidder to be guided by Clause 7.0 of Part-3, Section-III of SCC. |
| 5 |  | General |  |  | Impact of GST | Kindly clarify the reimbursement of impact of GST on the Contract Price which is not presently considered in the Bid estimate, and being a new Law coming into implementation. Also please clarify with respect to service tax which is presently reimbursed as per the existing clause. | Presently the tax implication is ED(0)+CST(2%) on Inter state +VAT(14.5%) on local goods. The proposed tax implication in GST will be (17%-18%). The bidders to indicate in their bid the following: 1. Value of Inter Sate Sale 2. Value of Local Sale 3. Value of Service If the above components are available, the differential amount can be calculated and reimbursed to the Contractor against proper documentary evidence. |
| 6 |  | Volume-1 | Commercial | Clause 62(iii) page 77/138 |  | Since any change in the taxes and duties are going to applicable to both the bidder and his vendors /sub-contractors , it is requested that the clause under 62(iii) may please be deleted , especially in view of GST coming into place as bidder presently has not considered the impact in their estimates at time of bidding . | The clause in the Tender is very clear, hence the bidder to be guided accordingly. |
| 7 |  | General |  |  |  | If for reasons not attributable to Bidder, the commissioning gets delayed, then suitable compensation of idling of the contractor may please provide for concluding by a mutual discussion on the same. | In case delay is attributable to the Company, the payments on account of retention on Commissioning and PGTR shall be paid against Bank Guarantee (BG) after 6(Six) months from the date of Commissioning. However in Force Majeure situation, it will be guided by the provision of Force Majeure clause in the Contract. |