| GENERAL |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | General | Vol- I , Commercial | Forwarding Letter. | 3.0,(v) | Bid Closing Date & Time | As there is no sufficient technical data available in the tender document, we request OIL India to extend the bid submission for 2 months from 15-09-2016. |  | Bid submission date has been extended upto 27.10.2016 (11.00 hrs. IST) through Corrigendum No.1 dated 07.09.2016 |
| PROCESS |  |  |  |  |  |  |  |  |
| 1 | Technical | GCS-PRS-001 | Process & Utility Description for Makum GCS | Sheet 6 of 18 | D. Two Phase Separator | Tender says to consider 1W+1S separator at suction and delivery of the gas. Bidder requests company to reconfirm the requirement of stand by separator as the same is not required as per bidder’s past experience. |  | It is OISD requirement |
| 2 | Technical | GCS-PRS-001 | Process & Utility Description for Makum GCS | Sheet 8 of 18 | J. Flare System | Bidder understands that the new flare header is to be connected to existing ground flare and no new flare stack is required. Kindly confirm. |  | New flare stack is not required, the flare to be connected at existing flare with connecting line line. |
| 3 | Technical | General | Process & Utility Description for Makum GCS |  | P&ID & PFD | Kindly provide the PFD’s & P&ID’s of the system. |  | Generation of PFD & P&ID is in bidder’s scope based on the tentative block flow diagram provided. Please read carefully the tender specification. |
| 4 | Technical | GCS-PRS-002 | Process Design Basis |  | Datasheet | Kindly provide the Datasheet of LP & GL compressors. |  | Provided in Specification for compressor in the tender specification |
| 5 | Technical | GCS-PRS-001 | Process Scope of Work | Sheet 10 of 18 | Inert Gas System | Kindly mention the Type of Inert gas system to be used. i.e. PSA system or cylinders with manifold. |  | Inert gas shall be N2 . Inert gas system is meant for purging of the equipments. |
| 6 | Technical | GCS-PRS-002 | Process Design Basis | Sheet 2 & 3 of 5 | GL Compressor Capacity | As per Cl. 3 of Process design basis, outlet gas quantity of HP compressor is 0.44 MMSCMD (17343 Nm3/hr), whereas as per Cl. 4, GL compressor capacity is 3200Nm3/hr. Bidder request company to mention the no. of compressors to achieve aforesaid O/L gas quantity. |  | The compressor configuration is as follows: LP Compressors= 2X3200NM3/hr + 1X5600NM3/hr + Future provision = 17343 NM3/hr HP Compressors= 3X2700 NM3/hr + Future provision =17343 NM3/hr |
| 7 | Technical | GCS-PRS-002/ GCS-PRS-001 | Process Design Basis / Process Scope of Work | Sheet 2 & 3 of 5 / Sheet 9 of 18 | Operating Philosophy of Compressor | As per cl. 5 of Process design basis, operation philosophy of compressors mentioned is 3 running which contradicts with the one described in cl. L of Scope of work as 2 running + 1 stand-by. Kindly Clarify |  | LP Compressor: 2X3200NM3/hr-Running 1X5600NM3/hr-S/By OR 1X3200NM3/hr-Running 1X5600NM3/hr- Running 1X3200NM3/hr- S/By OR 1X3200NM3/hr-Running 1X5600NM3/hr- Running 1X3200NM3/hr- Running HP Compressor: 2X2700 NM3/hr-Running 1X2700 NM3/hr-S/By OR 3X2700 NM3/hr-Running |
| 8 | Technical | GCS-PRS-002 | Process Design Basis | Sheet 2 & 3 of 5 | LP Compressor Capacity | As per Cl. 4, two different capacities of LP compressors are mentioned. Bidder requests client to provide the configuration of compressors to achieve the gas flow rate of 0.44 MMSCMD. |  | Refer to your query no 6 above. |
| Civil |  |  |  |  |  |  |  |  |
| 1 | Technical | GCS-CIV-001 | Civil & Structural Description for Makum GCS |  | Geo technical report |  | Please provide the geo technical report to understand the underlying soil strata. | It is in the scope of the bidder. |
| 2 | Technical | GCS-CIV-001 | Civil & Structural Description for Makum GCS |  | Topographical report |  | Please provide the topo graphical report of proposed site. | OIL will provide only MSL of the proposed plot and bidder to arrange the soil survey of the same. The bidder to estimate the soil estimate based on MSL & FGL of the plot. |
| 3 | Technical | GCS-CIV-001 | Civil & Structural Description for Makum GCS |  | Type of foundation |  | Bidder under stands that shallow foundations are enough for various facilities in proposed facilities. | The soil bearing capacity to be assumed as 10T/m2 maximum for bidding purpose. The detail soil testing is in the scope of successful bidder. If from the detail investigation, if the actual soil bearing capacity is more that 10T/m2, then 10T/m2 shall be considered for detail designing. However, if the actual value is found to be lower than 10T/M2 in that case the actual value shall be considered. |
| 4 | Technical | GCS-CIV-001 | Civil & Structural Description for Makum GCS | 1.7 | Meteorological data |  | Please provide the Metrological data to design storm water drains and to finalize the size of reservoir. | Metrological data enclosed in General Scope of Work in the tender specification. There is no disposal drain nearby for storm water drain, bidder to design storm water disposal pipeline size and disposal pump as per bid specification. The construction of disposal line is in outside the battery limit and beyond the scope of the bidder. |
| 5 | Technical | GCS-CIV-001 | Civil & Structural Description for Makum GCS | 2.0 | Buildings & Sheds |  | Please provide the plans of, tube well room, security room/Morcha, Fire water pump house, Gas compressor shed, Air compressor shed. | The design is in bidders scope complying petroleum industry standard. |
| 6 | Technical | GCS-CIV-001 | Civil & Structural Description for Makum GCS |  | Plot plan |  | Please provide the plot of proposed facilities. | It is in bidder’s scope. Bidder to design the plot-plan utilizing the minimum amount of land complying all the standards & applicable rules. OIL/OIL’s consultant will review the plot. |