## Pre-bid queries
Effuluent Treatment Plant in Tenkaghat, Assam
COMMERCIAL QUERIES
S No | Section | Vol & Page | Clause Description | Query | Clarifications by Client
14 | Part-3 - SECTION - III - SPECIAL CONDITIONS OF CONTRACT | 5.0 SUPPLY OF WATER, POWER & OTHER UTILITIES | Water, power and land for Contractor’s Office and site fabrication, Ware house, residential accommodation etc. shall be arranged by Contractor at noextra cost to Owner and the quoted prices shall deemed to be inclusive of such expenses, if any. OWNER shall provide land free from all encumbrances as per the Site map enclosed for Construction of Effluent Treatment Plant. Subject to availability, Construction Power shall be supplied by OWNER on chargeable basis at applicable rate. Power shall be provided at one point at worksite. Further distribution/ requirement from above shall be arranged by the contractor at his own cost, if any. Subject to availability, Construction water shall be supplied by OWNER to the Contractor on chargeable basis, (charges to be intimated later) at one point at worksite. Further distribution/ requirement from above shall be arranged by the contractor at his own cost, if any. | WATER AND POWER FOR TESTING AND COMMISSIONING TO BE PROVIDED FREE OF COST. | As already clarified in the Pre-bid query, the same is chargeable.
15 | Part-3 - SECTION - III - SPECIAL CONDITIONS OF CONTRACT | 12.0 FIRM PRICES | The quoted price shall remain firm and fixed till the completion of work except for the statutory variations of Taxes & Duties as mentioned elsewhere in the bidding document. | PRICE SHALL BE FIRM WITHIN THE CONTRACTUAL COMPLETION PERIOD AND IF THE DELAY IS ATTRIBUTABLE TO ADIPL. | Price shall be firm throughout the currency of the Contract in any situation.
16 | Part-3 - SECTION - III - SPECIAL CONDITIONS OF CONTRACT | 39.0 EXCAVATION BY BLASTING | The Contractor shall obtain licence from the District authorities for undertaking blasting work as well as for obtaining and storing the explosive as per Explosive Rules 1940, corrected up to date. He shall purchase the Explosives, fuses, detonators etc. only from a licensed dealer. He shall be responsible for the safe custody and proper accounting of the explosive materials. The Engineer-in-Charge and his authorised representative shall have the access to check the contractor's store of explosives and his accounts. In case where the explosive are required to be transported and stored at site, relevant clauses of the Explosive rules 1940 as amended subsequently shall apply. The Contractor shall be responsible for any accident to workman, public or property, due to blasting operations | HARDROCK EXCAVATION ENVISAGED DURING EXCAVATION SHALL BE ADDITIONAL PRICE. | Such situation is not likely to be encountered as the same has been assessed by many bidders during site visit. Therefore Bidder's view is not acceptable.
17 | ANNEXURE- II to Special Conditions of Contract | A) SCHEDULE OF PAYMENTS | Progressive Payments to Contractor shall be made for the activities as stated below to the extent of weightages mentioned against each on basis of EPC price (quoted vide Sl. 4 of Form SP-0. | IF PGTR / HANDING OVER IS DELAYED BY COMPANY FOR REASONS NOT ATTRIBUTABLE TO ADIPL THEN 5 % OF EPC PRICE TO BE RELEASED AGAINST BG. | No period of delay is specified by the bidder. In case, delay is more than 6 months from date of mechanical completion in such situation payment may be releaded against BG .