## PBQ
Pre Bid Commercial Query - Lot 1
Bidder Name -
Project Name - "Construction of Oil Collecting Station(OCS) at Barekuri/ Assam"
Client - Oil india Limited
IFB No.: CPG5284P15
Date : 08.12.2014
Sl. No. | Reference Of Bidding Document |  |  |  | Bidder's Query | Client's Response
| Part / Vol. | Page No. | Clause No. | Subject
1 | Part 3 -Section I | 43 | 6.8 | Warranty of Plant | In the event of commissioning of the plant is delayed due to reason solely attributable to Company then the cost of extended warranty shall be borne by the Company. Please Clarify. | Please consider the warranty requirements mentioned in tender for submitting your Proced Quotation. No additional prices than those indicated in the Bid shall aplly.
2 | Part 3 -Section I | 44 | 6.12 | Performance Guarantees | Performance Guarantees agreed by the Contractor is contingent to the input raw materials and utilities supplied/ provided by the Company , in event of any deviation in the input parameters the Contractor shall not be held responsible for any change or failure in meeting the performance factors agreed for the plants.Client to clearly specify the input parameters in technical responses. Please confirm. | Bidder to follow input parameters provided in the process design basis and elsewhere in the tender and provide performance gurantees accordingly.
3 | Part 3 -Section I | 50 | 9.7.2 | Deemed Export Benefit | In the event of terminal excise benefit is not available/applicable for certain items the same shall be paid separately , please confirm. | The deemed export benefits are available as per Exim policy mentioned in the clause. Bidder is requested to check latest position in this regard as per Clause 9.9 with an expert in the field. OIL will not bear any extra Cost / Responsibility for incorrect assessment of available benefits by Contractor.
4 | Part 3 -Section I | 52 | 11.2 | Changes in Work | Bidder understand that in event of any changes to the work the Change Order issued will include the cost and time required for execution of such changes. Please confirm. | Agree in principle.
5 | Part 3 -Section I | 57 | 14.1 | Arbitration | In case of Sole Arbitration the appointment of Sole Arbitrator shall be a person mutually acceptable to both the parties. Please confirm. | Change in Clause not acceptable. Please follow Tender document.
7 | Part 3 -Section III | 132 | 1.0 p | Notice | Bidder suggest that email to be also included as a medium of giving a notice . | Not agreed.
8 | Part 3 -Section III | 142 | 17 | Release of Payment | Bidder requests that the the Payment stages mentioned under Section -IV be made according to mutually acceptable stages , as the current stages locks up considerable amount upto commissioning date which will have adverse impact on the cash flow required for the smooth running of the Project. Please Confirm. | Follow bidding document.
9 | Part 3 -Section III | 144 | 18 | Mobilisation Advance | Bidder request Interest free Mobilisation Advance to be provided as the advance is required to meet the high initial mobilisation cost of labour and equipment and also the procurement cost of materials. | Not permitted as per prevailing guideliness followed by Company.
10 | Addition |  |  | Extension of Time Provision | Bidder request the Client to provide Extension of Time provision in the contract as the same is missing in the Contract. | Contractor is expected to adhere to the time schedule stipulated. Extension, if warranted, during the course of execution shall be dealt with as deemed fit.
11 | Payment Schedule | 165/266 | Part 3 Section IV | Service Line Item No. 20 | Bidder request Client to revise the cap(Payment limited to) for PROCUREMENT to 55% instead of 40% | Oil will review and revert. Changes if any, shall be notified in addendum to tender.
12 | Payment Schedule | 165/266 | Part 3 Section IV | Service Line Item No. 210 & 220 Sl.No. 8 and Sl.no.9 | Bidder also request deletion of clause for payment of "10% against BG ………receipt of material at site and acceptance". | Not acceptable. Follow bidding document.
13 | Payment Schedule | 165/266 | Part 3 Section IV | Service Line Item No. 30 | Bidder request Client to revise the cap (Payment limited to) for CONSTRUCTION and COMMISSIONING to 45% instead of 40% | Oil will review and revert. Changes if any, shall be notified in addendum to tender.
14 | Payment Schedule | 167/266 | Part 3 Section IV | Service Line Item No. 40 | Bidder request Client to revise the cap (Payment limited to) for PGTR to 5% instead of 10% | Oil will review and revert. Changes if any, shall be notified in addendum to tender.