## Combined TQ-1
Pre-Bid Clarifications for Hiring of Services for Engineering, Procurement and Construction (EPC) of Oil Collecting Station (OCS) at Barekuri, Assam on Lumpsum Turnkey basis of “M/s. OIL India Limited”
Tender No: CPG5284P15
Bidder |  |  |  |  | TQ-2 dated 09.12.2014
Sr. No. | Bid Reference |  |  |  | Bidder's Queries / Observation / Comments | OIL Response
| Description | Section | Document No. | Clause
Commercial
1 | Release of Payment | Instruction to Bidder | Clause 6.8 of WARRANTY AND REMEDY OF DEFECTS and Milestone Sr. no. C, 18, |  | Please refer Clause 6.7 & 6.8, wherein it is mentioned as: Clause 6.8 states that :: "In case the commissioning is delayed due to the reason solely attributable to Company, whereas the plant has been completed and made ready for Commissioning by the Contractor, such warranty/guarantee shall be valid for a period of 24 (Twenty Four months reckoned from the date of plant is made ready for commissioning or 12 (twelve) months from the date of issue of Certificate of Completion and acceptance, whichever is earlier". Based on above please clarify the followings: ( a) When Completion Certificate will be issued to contractor i.e. after the plant has been completed by the Contractor OR made ready for Commissioning by the Contractor OR after Commissioning of the plant? ( b ) If the commissioning is delayed due to the reason solely attributable to Company, when the payment against milestone Sr. No. C-18 for Successful Commissioning of OCS (7%) will be released ? | (a) Completion certificate will be issued after trouble free trial run of 3 months. (b) Please refer discussion in Pre-Bid conference where OIL confirmed the ready availability of Crude Oil flowlines from Wells for immediate hook up to the OCS as soon as it is ready and hence no delay in COmmissioning on this is envisaged
2 | Payment | Instruction to Bidder | Clause 6.8 of WARRANTY AND REMEDY OF DEFECTS and Milestone Sr. No. 40, 20 |  | Please refer Clause 6.7 & 6.8, wherein it is mentioned as: Clause 6.8 states that :: "In case the commissioning is delayed due to the reason solely attributable to Company, whereas the plant has been completed and made ready for Commissioning by the Contractor, such warranty/guarantee shall be valid for a period of 24 (Twenty Four months reckoned from the date of plant is made ready for commissioning or 12 (twelve) months from the date of issue of Certificate of Completion and acceptance, whichever is earlier". Please clarify if the commissioning is delayed due to the reason solely attributable to Company when the payment against milestone Sr. No.D-40 for PGTR Successful Trial run of the OCS (40% of 10% of LSTK Price) will be released ? | Refer explaination in Sr. No. 1 above
3 | Compensation | Instruction to Bidder | Clause 6.0 and 6.7, 6.8 of WARRANTY AND REMEDY OF DEFECTS |  | Please refer Clause 6.7 & 6.8, wherein it is mentioned as: Clause 6.8 states that :: "In case the commissioning is delayed due to the reason solely attributable to Company, whereas the plant has been completed and made ready for Commissioning by the Contractor, such warranty/guarantee shall be valid for a period of 24 (Twenty Four months reckoned from the date of plant is made ready for commissioning or 12 (twelve) months from the date of issue of Certificate of Completion and acceptance, whichever is earlier". Please clarify that if the commissioning is delayed due to the reason solely attributable to Company how contractor shall be compensated for extended stay? | Refer explaination in Sr. No. 1 above
4 | Duration of the Contract |  | Invitation For Bid (IFB) |  | Please refer to IFB wherein duration of contract is mentioned as "For engineering, supply, construction & erection of the OCS on LSTK basis: 21 months from the date of LOA , For trial run & commissioning of the OCS: 3 months". This job includes supply of long lead items such as Bath Heaters, Compressor package etc. Also construction period in a year in Assam is very narrow. Hence, we request OIL to kindly reconsider the Project completion schedule and may be enhanced from 21 months + 3 month Trial run to 30 months + 3 months Trial run. | Follow bidding document. Proposal for revision in completion schedule is not acceptable.
5 | Time Extension in submission of Bid. |  |  |  | There are many equipments whose technical details are not available with the bid documents. Vendor will not provide their inputs untill those documents are available to them. Hence we request you to kindly extend the submission of bid by 4 weeks. | Noted and will be considered suitably.