## Summary
DISCIPLINE | Code-1 | Code-2 | Code-3 | Code-4 | Deleted | Submitted | Balance | Grand Total
Civil | 52 | 12 | 11 | 8 | 19 | 36 | 31 | 169
Electrical | 34 | 1 | 4 |  | 1 | 16 | 2 | 58
General / Projects | 2 | [6 empty] | 2
Instrumentation & Telecom | 10 | 49 |  |  | 9 | 10 | 5 | 83
Mechanical | 39 | 6 | 7 |  | 1 | 6 |  | 59
Piping | 7 | 6 | 2 |  | 1 | 1 | 14 | 31
Process | 27 | 37 | 1 |  |  |  | 3 | 68
Safety | 29 | 4 | 1 |  |  |  |  | 34
Grand Total | 200 | 115 | 26 | 8 | 31 | 69 | 55 | 504
General / Projects | [7 empty] | 3
507

## DCI MCI
DCI-MCI OF GAS COMPRESSOR STATION AT MAKUM, ASSAM
C1
c | DCI/MCI | DISCIPLINE | DOCUMENT No. | DOCUMENT NAME | CODE | Current Status Code | With X | For N Days | Remarks | Planned | Sr.No. as per Billing Schedule
1 | DCI | General / Projects | P4007-PM-DCI-001 | Document Control Index | A | 1 | COMPLETE | #VALUE! |  | 2017-11-24 | 1 | #N/A | Code-1
2 | DCI | General / Projects | P4007-PM-MCI-001 | Material Control Index | A | 1 | COMPLETE | #VALUE! |  | 2017-11-24 | 2 | #N/A | Code-1
3 | DCI | General / Projects | P4007-PM-MCI-002 | AS-Built Drawings | A |  | Rejected | #VALUE! |  | 2018-10-23 | 3 | #N/A | #N/A
4 | DCI | Process | P4007-PR-DB-001 | Process Design Basis | A | 2 | COMPLETE | #VALUE! |  | 2017-12-01 | 4 | #N/A | Code-2
5 | DCI | Process | GCS-PRPF0001 | Process Flow Diagram | A | 2 | COMPLETE | #VALUE! |  | 2017-12-01 | 5 | #N/A | Code-2
6 | DCI | Process | GCS-PRUF0002 | Utility Flow Diagram | A | 2 | COMPLETE | #VALUE! |  | 2017-12-01 | 6 | #N/A | Code-2
7 | DCI | Process | GCS-PRCE0001 | Cause & Effect Drawings | A | 2 | COMPLETE | #VALUE! |  | 2018-01-04 | 7 | #N/A | Code-2
8 | DCI | Process | GCS-PRHE0001 | Heat & Material Balance | A | 1 | COMPLETE | #VALUE! |  | 2017-12-01 | 8 | #N/A | Code-1
9 | DCI | Process | GCS-PRPD0001 | P&ID - Legend (Sheets 1 to 5) | A | 2 | COMPLETE | #VALUE! |  | 2018-01-02 | 9 | #N/A | Code-2
10 | DCI | Process | GCS-PRPD0002 | P&ID - Gas Reception | A | 2 | COMPLETE | #VALUE! |  | 2018-01-02 | 10 | #N/A | Code-2
11 | DCI | Process | GCS-PRPD0003 | P&ID - LP Gas Knockout Drums | A | 2 | COMPLETE | #VALUE! |  | 2018-01-02 | 11 | #N/A | Code-2
12 | DCI | Process | GCS-PRPD0004 | P&ID - Mist Extractor | A | 2 | COMPLETE | #VALUE! |  | 2018-01-02 | 12 | #N/A | Code-2
13 | DCI | Process | GCS-PRPD0005 | P&ID - LP Compressor Module - A, B & C (Sheets 1 to 3) | A | 2 | COMPLETE | #VALUE! |  | 2018-01-02 | 13 | #N/A | Code-2
14 | DCI | Process | GCS-PRPD0006 | P&ID - MP Gas Grid | A | 2 | COMPLETE | #VALUE! |  | 2018-01-02 | 14 | #N/A | Code-2
15 | DCI | Process | GCS-PRPD0007 | P&ID - MP Gas Knockout Drums | A | 2 | COMPLETE | #VALUE! |  | 2018-01-02 | 15 | #N/A | Code-2
16 | DCI | Process | GCS-PRPD0008 | P&ID - Coalescer Filter | A | 2 | COMPLETE | #VALUE! |  | 2018-01-02 | 16 | #N/A | Code-2
17 | DCI | Process | GCS-PRPD0009 | P&ID - Gas Dehydration Unit | A | 2 | COMPLETE | #VALUE! |  | 2018-01-02 | 17 | #N/A | Code-2
18 | DCI | Process | GCS-PRPD0010 | P&ID -HP Compressor Module - A,B & C (Sheets 1 to 3) | A | 2 | COMPLETE | #VALUE! |  | 2018-01-02 | 18 | #N/A | Code-2
19 | DCI | Process | GCS-PRPD0011 | P&ID - HP Gas KnockOut Drums | A | 2 | COMPLETE | #VALUE! |  | 2018-01-02 | 19 | #N/A | Code-2
20 | DCI | Process | GCS-PRPD0012 | P&ID - Gas Lift Header | A | 2 | COMPLETE | #VALUE! |  | 2018-01-05 | 20 | #N/A | Code-2
21 | DCI | Process | GCS-PRPD0013 | P&ID - Fuel Gas Conditioning Package | A | 2 | COMPLETE | #VALUE! |  | 2018-01-05 | 21 | #N/A | Code-2
22 | DCI | Process | GCS-PRPD0014 | P&ID - Methaol Injection Skid | A | 2 | COMPLETE | #VALUE! |  | 2018-01-05 | 22 | #N/A | Code-2
23 | DCI | Process | GCS-PRPD0015 | P&ID - Instrument / Plant Air | A | 2 | COMPLETE | #VALUE! |  | 2018-01-05 | 23 | #N/A | Code-2
24 | DCI | Process | GCS-PRPD0016 | P&ID - Service Water System (Borewell and sump & Water softener and distribution) | A | 2 | COMPLETE | #VALUE! |  | 2018-01-05 | 24 | #N/A | Code-2
25 | DCI | Process | GCS-PRPD0017 | P&ID - Potable Water Package | A | 2 | COMPLETE | #VALUE! |  | 2018-01-05 | 25 | #N/A | Code-2
26 | DCI | Process | GCS-PRPD0018 | P&ID - Power Generation | A | 2 | COMPLETE | #VALUE! |  | 2018-01-05 | 26 | #N/A | Code-2
27 | DCI | Process | GCS-PRPD0020 | P&ID - Flare System | A | 2 | COMPLETE | #VALUE! |  | 2018-01-05 | 28 | #N/A | Code-2
28 | DCI | Process | GCS-PRPD0021 | P&ID - Closed Blow Down System | A | 2 | COMPLETE | #VALUE! |  | 2018-01-05 | 29 | #N/A | Code-2
29 | DCI | Process | GCS-PRPD0022 | P&ID - Effluent Treatment Package | A | 2 | COMPLETE | #VALUE! |  | 2018-01-05 | 30 | #N/A | Code-2
30 | DCI | Process | GCS-PRPD0023 | P&ID - Oily Water System | A | 2 | COMPLETE | #VALUE! |  | 2018-01-05 | 31 | #N/A | Code-2
31 | DCI | Process | GCS-PRPD0024 | P&ID - Contaminated Rain Water System | A | 2 | COMPLETE | #VALUE! | #VALUE! | 2018-01-05 | 32 | #N/A | Code-2
32 | DCI | Process | GCS-PRPD0025 | P&ID - Inert Gas Distribution System | A | 2 | COMPLETE | #VALUE! |  | 2018-01-05 | 33 | #N/A | Code-2
33 | DCI | Process | P4007-PR-DS-001 | Process Datasheet- LP Gas Knockout Drum | A | 1 | COMPLETE | #VALUE! |  | 2018-01-04 | 34 | #N/A | Code-1
34 | DCI | Process | P4007-PR-DS-002 | Process Datasheet-LP Compressor Package | A | 1 | COMPLETE | #VALUE! |  | 2018-01-02 | 35 | #N/A | Code-1
35 | DCI | Process | P4007-PR-DS-003 | Process Datasheet-MP Gas Knockout Drum | A | 1 | COMPLETE | #VALUE! |  | 2018-01-04 | 36 | #N/A | Code-1
36 | DCI | Process | P4007-PR-DS-004 | Process Datasheet-Filter Coalescer | A | 1 | COMPLETE | #VALUE! |  | 2018-01-05 | 37 | #N/A | Code-1
37 | DCI | Process | P4007-PR-DS-005 | Process Datasheet-Dehydration Package | A | 1 | COMPLETE | #VALUE! |  | 2017-12-29 | 38 | #N/A | Code-1
38 | DCI | Process | P4007-PR-DS-006 | Process Datasheet-Fuel Gas System | A | 1 | COMPLETE | #VALUE! |  | 2018-01-05 | 39 | #N/A | Code-1
39 | DCI | Process | P4007-PR-DS-007 | Process Datasheet-HP Compressor Package | A | 1 | COMPLETE | #VALUE! |  | 2018-01-02 | 40 | #N/A | Code-1
40 | DCI | Process | P4007-PR-DS-008 | Process Datasheet-HP Gas Knockout Drum | A | 1 | COMPLETE | #VALUE! |  | 2018-01-04 | 41 | #N/A | Code-1
41 | DCI | Process | P4007-PR-DS-009 | Process Datasheet-Flare Knockout Drum | A | 2 | COMPLETE | #VALUE! |  | 2018-09-25 | 42 | #N/A | Code-2
42 | DCI | Process | P4007-PR-DS-010 | Process Datasheet - Flare Knockout Pumps | A | 2 | COMPLETE | #VALUE! |  | 2018-09-25 | 43 | #N/A | Code-2
43 | DCI | Process | P4007-PR-DS-011 | Process Datasheet-Closed Blown down System | A | 2 | COMPLETE | #VALUE! |  | 2018-10-05 | 44 | #N/A | Submitted
44 | DCI | Process | P4007-PR-DS-012 | Process Datasheet-ETP System | A | 1 | COMPLETE | #VALUE! |  | 2018-01-08 | 45 | #N/A | Code-1
45 | DCI | Process | P4007-PR-DS-013 | Process Datasheet-Service Water System | A | 1 | COMPLETE | #VALUE! | #VALUE! | 2018-02-02 | 46 | #N/A | Code-1
46 | DCI | Process | P4007-PR-DS-014 | Process Datasheet-Potable Water System | A | 1 | COMPLETE | #VALUE! |  | 2018-02-02 | 47 | #N/A | Code-1
47 | DCI | Process | P4007-PR-DS-015 | Process Datasheet-Methanol Dosing Package | A | 1 | COMPLETE | #VALUE! |  | 2018-01-12 | 48 | #N/A | Code-1
48 | DCI | Process | P4007-PR-DS-016 | Process Datasheet-Fire Water Tanks | A | 1 | COMPLETE | #VALUE! |  | 2018-03-02 | 49 | #N/A | Code-1
49 | DCI | Process | P4007-PR-DS-017 | Process Datasheet-Fire Water Pumps | A | 1 | COMPLETE | #VALUE! |  | 2018-02-23 | 50 | #N/A | Code-1
50 | DCI | Process | P4007-PR-DS-018 | Process Datasheet-Oil-in Water system | A | 2 | COMPLETE | #VALUE! |  | 2018-10-05 | 51 | #N/A | Code-2
51 | DCI | Process | P4007-PR-DS-019 | Process Datasheet-Condensate Loading Pumps | A | 1 | COMPLETE | #VALUE! |  | 2018-02-09 | 52 | #N/A | Code-1
52 | DCI | Process | P4007-PR-DS-020 | Process Datasheet-Effluent Water Transfer Pumps | A | 1 | COMPLETE | #VALUE! |  | 2018-02-16 | 53 | #N/A | Code-1
53 | DCI | Process | P4007-PR-DS-021 | Process Datasheet-Bore Well Pump | A | 1 | COMPLETE | #VALUE! |  | 2018-02-16 | 54 | #N/A | Code-1
54 | DCI | Process | P4007-PR-DS-022 | Process Datasheet-Effluent Water Disposal Pumps | A | 1 | COMPLETE | #VALUE! |  | 2018-02-16 | 55 | #N/A | Code-1
55 | DCI | Process | P4007-PR-DS-023 | Process Datasheet-Effluent Water Storage Tank | A | 1 | COMPLETE | #VALUE! |  | 2018-02-16 | 56 | #N/A | Code-1
56 | DCI | Process | P4007-PR-DS-024 | Process Datasheet - Instrument Air Compressor Package | A | 2 | COMPLETE | #VALUE! |  | 2018-01-19 | 57 | #N/A | Code-2
57 | DCI | Process | P4007-PR-DS-025 | Process Datasheet - Jockey Pump | A | 1 | COMPLETE | #VALUE! |  | 2018-02-16 | 58 | #N/A | Code-1
58 | DCI | Process | P4007-PR-DS-026 | Process Datasheet- Mist Extractor | A | 1 | COMPLETE | #VALUE! |  | 2018-01-05 | 59 | #N/A | Code-1
59 | DCI | Process | P4007-PR-DS-027 | Process Datasheet- Inert Gas Generation Package | A | 1 | COMPLETE | #VALUE! |  | 2018-04-19 | 60 | #N/A | Code-1
60 | DCI | Process | P4007-PR-PY-001 | Process Description & Control Philosophy | A | 1 | COMPLETE | #VALUE! | #VALUE! | 2017-12-29 | 61 | #N/A | Code-1
61 | DCI | Process | P4007-PR-RP-001 | Process Simulation Report | A | 1 | COMPLETE | #VALUE! |  | 2018-01-04 | 62 | #N/A | Code-1
62 | DCI | Process | P4007-PR-RP-002 | Line Size Calculation | A | 1 | COMPLETE | #VALUE! |  | 2018-01-08 | 63 | #N/A | Code-1
63 | DCI | Process | P4007-PR-RP-003 | Equipment Sizing Calculation | A | 2 | COMPLETE | #VALUE! |  | 2018-01-17 | 64 | #N/A | Code-2
64 | DCI | Process | P4007-PR-RP-004 | Flare & Blow down Study Report | A |  | Rejected | #VALUE! |  | 2018-09-27 | 65 | #N/A | NS
65 | DCI | Process | P4007-PR-RP-005 | Fire Water demand and Network Analysis | A | 1 | COMPLETE | #VALUE! |  | 2018-02-16 | 66 | #N/A | Code-1
66 | DCI | Process | P4007-PR-RP-006 | Line List | I | 2 | COMPLETE | #VALUE! |  | 2018-02-16 | 67 | #N/A | Code-2
67 | DCI | Process | P4007-PR-RP-007 | Utility & Effluent Summary | I | 3 | Rejected | #VALUE! | #VALUE! | 2018-01-10 | 68 | #N/A | Code-3
68 | DCI | Process | P4007-PR-RP-008 | Alarm & Trip Schedule | A | 2 | COMPLETE | #VALUE! | #VALUE! | 2018-02-09 | 69 | #N/A | Code-2
69 | DCI | Process | P4007-PR-RP-009 | Operating Manual | I |  | Rejected | #VALUE! |  | 2018-11-02 | 70 | #N/A | NS
70 | DCI | Process | P4007-PR-RP-010 | Pre-commissioning, Commissioning Manual | I |  | Rejected | #VALUE! |  | 2018-11-09 | 71 | #N/A | NS
71 | DCI | Process | P4007-PR-RP-011 | Equipment List | I | 2 | COMPLETE | #VALUE! |  | 2018-01-03 | 72 | #N/A | Code-2
72 | DCI | Mechanical | P4007-ME-DB-001 | Mechanical Design Basis | A | 1 | COMPLETE | #VALUE! |  | 2017-12-01 | 73 | #N/A | Code-1
73 | DCI | Mechanical | P4007-ME-DS-001 | Mechanical Datasheet-LP Gas KOD | A | 1 | COMPLETE | #VALUE! |  | 2018-01-05 | 74 | #N/A | Code-1
74 | DCI | Mechanical | P4007-ME-DS-002 | Mechanical Datasheet-LP Gas Booster Compressor Package | A | 1 | COMPLETE | #VALUE! |  | 2018-01-03 | 75 | #N/A | Code-1
75 | DCI | Mechanical | P4007-ME-DS-003 | Mechanical Datasheet-MP Gas KOD | A | 1 | COMPLETE | #VALUE! |  | 2018-01-05 | 76 | #N/A | Code-1
76 | DCI | Mechanical | P4007-ME-DS-004 | Mechanical Datasheet-Filter Coalescer | A | 1 | COMPLETE | #VALUE! |  | 2018-01-08 | 77 | #N/A | Code-1
77 | DCI | Mechanical | P4007-ME-DS-005 | Mechanical Datasheet-Dehydration Package | A | 1 | COMPLETE | #VALUE! |  | 2018-01-03 | 78 | #N/A | Code-1
78 | DCI | Mechanical | P4007-ME-DS-006 | Mechanical Datasheet-Fuel Gas System | A | 1 | COMPLETE | #VALUE! |  | 2018-01-12 | 79 | #N/A | Code-1
79 | DCI | Mechanical | P4007-ME-DS-007 | Mechanical Datasheet-HP Gas Lift Compressor Package | A | 1 | COMPLETE | #VALUE! |  | 2018-01-04 | 80 | #N/A | Code-1
80 | DCI | Mechanical | P4007-ME-DS-008 | Mechanical Datasheet-HP Gas KOD | A | 1 | COMPLETE | #VALUE! |  | 2018-01-05 | 81 | #N/A | Code-1
81 | DCI | Mechanical | P4007-ME-DS-009 | Mechanical Datasheet-Flare KOD | A | 1 | COMPLETE | #VALUE! | #VALUE! | 2018-01-25 | 82 | #N/A | Code-1
82 | DCI | Mechanical | P4007-ME-DS-010 | Mechanical Datasheet -Flare KO Pumps | A | 1 | COMPLETE | #VALUE! | #VALUE! | 2018-01-29 | 83 | #N/A | Code-1
83 | DCI | Mechanical | P4007-ME-DS-011 | Mechanical Datasheet-Closed Blown down System | A | 1 | COMPLETE | #VALUE! |  | 2018-10-05 | 84 | #N/A | Code-1
84 | DCI | Mechanical | P4007-ME-DS-012 | Mechanical Datasheet-ETP System | A | 1 | COMPLETE | #VALUE! |  | 2018-01-10 | 85 | #N/A | Code-1
85 | DCI | Mechanical | P4007-ME-DS-013 | Mechanical Datasheet-Service Water System | A | 1 | COMPLETE | #VALUE! | #VALUE! | 2018-02-07 | 86 | #N/A | Code-1
86 | DCI | Mechanical | P4007-ME-DS-014 | Mechanical Datasheet-Potable Water System | A | 1 | COMPLETE | #VALUE! | #VALUE! | 2018-02-08 | 87 | #N/A | Code-1
87 | DCI | Mechanical | P4007-ME-DS-015 | Mechanical Datasheet-Methanol Dosing Package | A | 1 | COMPLETE | #VALUE! |  | 2018-01-19 | 88 | #N/A | Code-1
88 | DCI | Mechanical | P4007-ME-DS-016 | Mechanical Datasheet-Fire Water Tanks | A | 1 | COMPLETE | #VALUE! |  | 2018-03-06 | 89 | #N/A | Code-1
89 | DCI | Mechanical | P4007-ME-DS-017 | Mechanical Datasheet-Fire Water Pumps | A | 3 | Rejected | #VALUE! | #VALUE! | 2018-02-26 | 90 | #N/A | Code-3
90 | DCI | Mechanical | P4007-ME-DS-018 | Mechanical Datasheet-Oily Water system | A | 1 | COMPLETE | #VALUE! | #VALUE! | 2018-02-13 | 91 | #N/A | Code-1
91 | DCI | Mechanical | P4007-ME-DS-019 | Mechanical Datasheet-Condensate Loading Pumps | A | 3 | Rejected | #VALUE! |  | 2018-09-25 | 92 | #N/A | Code-3
92 | DCI | Mechanical | P4007-ME-DS-020 | Mechanical Datasheet-Effluent Water Transfer Pumps | A | 2 | COMPLETE | #VALUE! |  | 2018-09-27 | 93 | #N/A | Code-2
93 | DCI | Mechanical | P4007-ME-DS-021 | Mechanical Datasheet-Bore Well Pump | A | 1 | COMPLETE | #VALUE! |  | 2018-02-20 | 94 | #N/A | Code-1
94 | DCI | Mechanical | P4007-ME-DS-022 | Mechanical Datasheet-Effluent Water Disposal Pumps | A | 1 | COMPLETE | #VALUE! | #VALUE! | 2018-02-21 | 95 | #N/A | Code-1
95 | DCI | Mechanical | P4007-ME-DS-023 | Mechanical Datasheet-Effluent Water Storage Tank | A | 1 | COMPLETE | #VALUE! |  | 2018-02-22 | 96 | #N/A | Code-1
96 | DCI | Mechanical | P4007-ME-DS-024 | Mechanical Datasheet - Air Compressor Package | A | 3 | Rejected | #VALUE! | #VALUE! | 2018-01-23 | 97 | #N/A | Code-3
| DCI | Mechanical | P4007-ME-DS-025 | Mechanical Datasheet - Jockey Pump | A | 3 | Rejected | #VALUE! | #VALUE! | 2018-02-20 | 98 | #N/A | Code-3
98 | DCI | Mechanical | P4007-ME-DS-026 | Mechanical Datasheet- Mist Extractor | A | 1 | COMPLETE | #VALUE! |  | 2018-01-06 | 99 | #N/A | Code-1
99 | DCI | Mechanical | P4007-ME-DS-027 | Mechanical Datasheet- Gas Engine Power Generator System | A | 1 | COMPLETE | #VALUE! | Delayed due to no fronts from electrical | 2018-01-11 | 100 | #N/A | Code-1
100 | DCI | Mechanical | P4007-ME-DS-028 | Mechanical Datasheet- Emergency Diesel Generator System | A | 1 | COMPLETE | #VALUE! | #VALUE! | 2018-01-16 | 101 | #N/A | Code-1
101 | DCI | Mechanical | P4007-ME-DS-029 | Mechanical Datasheet- HOT Crane -(Maintenance & Compressor Building) | A | Submitted | Rejected | #VALUE! |  | 2018-09-25 | 102 | #N/A | Submitted
102 | DCI | Mechanical | P4007-ME-DS-031 | Mechanical Datasheet- Service Water Storage Tank | A | 1 | COMPLETE | #VALUE! |  | 2018-02-10 | 103 | #N/A | Code-1
103 | DCI | Mechanical | P4007-ME-DS-032 | Mechanical Datasheet- Potable Water Storage Tank | A | 1 | COMPLETE | #VALUE! |  | 2018-02-09 | 104 | #N/A | Code-1
104 | DCI | Mechanical | P4007-ME-DS-033 | Mechanical Datasheet- Inert Gas Generation Package | A | 1 | COMPLETE | #VALUE! | #VALUE! | 2018-06-22 | 105 | #N/A | Code-1
105 | DCI | Mechanical | P4007-ME-DS-034 | Mechanical Datasheet – Oily water system water pumps | A | 1 | COMPLETE | #VALUE! | #VALUE! | 2018-06-22 | 106 | #N/A | Code-1
106 | DCI | Mechanical | P4007-ME-DS-035 | Mechanical Datasheet – Service water pumps | A | 1 | COMPLETE | #VALUE! | #VALUE! | 2018-06-22 | 107 | #N/A | Code-1
107 | DCI | Mechanical | P4007-ME-DS-036 | Mechanical Datasheet – Sump tank pumps | A | 1 | COMPLETE | #VALUE! | #VALUE! | 2018-06-22 | 108 | #N/A | Code-1
108 | DCI | Mechanical | P4007-ME-RP-001 | Design Report - Fire Water Storage Tank | A | 1 | COMPLETE | #VALUE! |  | 2018-09-21 | 109 | #N/A | Code-1
109 | DCI | Mechanical | GCS-MEDD0001 | GAD - Fire Water Storage Tank | A | 1 | COMPLETE | #VALUE! |  | 2018-08-31 | 110 | #N/A | Code-1
110 | DCI | Piping | P4007-PI-DB-001 | Piping Design Basis | A | 1 | COMPLETE | #VALUE! |  | 2017-12-01 | 111 | #N/A | Code-1
111 | DCI | Piping | P4007-PI-PY-001 | Pipe Stress Analysis Philosophy | A | 1 | COMPLETE | #VALUE! | OIL Comment delay | 2017-12-22 | 112 | #N/A | Code-1
112 | DCI | Piping | P4007-PI-RP-001 | Pipe Stress & Flexibility Analysis Report - System 1 | A |  | Rejected | #VALUE! |  | 2018-10-12 | 113 | #N/A | NS
113 | DCI | Piping | P4007-PI-RP-002 | Pipe Stress & Flexibility Analysis Report - System 2 | A |  | Rejected | #VALUE! |  | 2018-10-16 | 114 | #N/A | NS
114 | DCI | Piping | P4007-PI-RP-003 | Pipe Stress & Flexibility Analysis Report - System 3 | A |  | Rejected | #VALUE! |  | 2018-10-18 | 115 | #N/A | NS
115 | DCI | Piping | P4007-PI-RP-004 | Pipe Stress & Flexibility Analysis Report - System 4 | A |  | Rejected | #VALUE! |  | 2018-10-19 | 116 | #N/A | NS
116 | DCI | Piping | P4007-PI-RP-005 | Pipe Stress & Flexibility Analysis Report - System 5 | A |  | Rejected | #VALUE! |  | 2018-10-23 | 117 | #N/A | NS
117 | DCI | Piping | P4007-PI-RP-006 | Pipe Stress & Flexibility Analysis Report - System 6 | A |  | Rejected | #VALUE! |  | 2018-10-23 | 118 | #N/A | NS
118 | DCI | Piping | P4007-PI-RP-007 | Pipe Stress & Flexibility Analysis Report - System 7 | A |  | Rejected | #VALUE! |  | 2018-10-25 | 119 | #N/A | NS
119 | DCI | Piping | P4007-PI-RP-008 | Pipe Stress & Flexibility Analysis Report - System 8 | A |  | Rejected | #VALUE! |  | 2018-10-26 | 120 | #N/A | NS
120 | DCI | Piping | P4007-PI-RP-009 | Critical Line List | I | 3 | Rejected | #VALUE! | #VALUE! | 2018-03-01 | 121 | #N/A | Code-3
121 | DCI | Piping | P4007-PI-RP-010 | Pipe Thickness Calculation Report | A | 2 | COMPLETE | #VALUE! | #VALUE! | 2018-01-10 | 122 | #N/A | Code-2
122 | DCI | Piping | P4007-PI-SP-001 | Piping Material specification | A | 1 | COMPLETE | #VALUE! |  | 2018-01-05 | 123 | #N/A | Code-1
123 | DCI | Piping | P4007-PI-SP-002 | Valve Material specification | A | 1 | COMPLETE | #VALUE! |  | 2018-01-08 | 124 | #N/A | Code-1
124 | DCI | Piping | P4007-PI-SP-003 | Painting Specification | A | 2 | COMPLETE | #VALUE! | #VALUE! | 2018-01-12 | 125 | #N/A | Code-2
125 | DCI | Piping | P4007-PI-SP-004 | Insulation Specfication | A | 2 | COMPLETE | #VALUE! | #VALUE! | 2018-01-12 | 126 | #N/A | Code-2
126 | DCI | Piping | P4007-PI-SP-005 | Pipe Support Standard | A | 1 | COMPLETE | #VALUE! |  | 2018-03-19 | 127 | #N/A | Code-1
127 | DCI | Piping | P4007-PI-GN-001 | PDMS 3D Model Design Review Guidelines | I | 2 | COMPLETE | #VALUE! | Sent by mail | 2018-01-05 | 128 | #N/A | Code-2
128 | DCI | Piping | P4007-PI-GN-002 | 30% PDMS MODEL REVIEW REPORT | I | 1 | COMPLETE | #VALUE! | #VALUE! | 2018-03-30 | 129 | #N/A | #N/A
129 | DCI | Piping | - | 3D Model (PDMS) - Model Review (30%, 60% & 90%) | A |  | Rejected | #VALUE! |  | 2018-10-26 | 130 | #N/A | NS
130 | DCI | Piping | GCS-PIDD0001 | Piping General Arrangement Drawings (GADs) | A |  | Rejected | #VALUE! |  | 2018-11-23 | 131 | #N/A | NS
131 | DCI | Piping | GCS-PIDD0002 | Pipe Support Detail Drawings | A |  | Rejected | #VALUE! |  | 2018-11-12 | 132 | #N/A | NS
132 | DCI | Piping | GCS-PIDD0003 | Pipe Support GADs | A | Deleted | Rejected | #VALUE! |  | 2018-11-16 | 133 | #N/A | #N/A
133 | DCI | Piping | GCS-PIIS0001 | Piping ISO Drawing | I |  | Rejected | #VALUE! |  | 2018-11-09 | 134 | #N/A | NS
134 | DCI | Piping | GCS-PILY0002 | Equipment Layout | A | 3 | Rejected | #VALUE! | #VALUE! | 2018-01-12 | 135 | #N/A | Code-3
135 | DCI | Civil | P4007-CV-DB-001 | Civil Design Basis | A | 1 | COMPLETE | #VALUE! |  | 2017-12-01 | 136 | #N/A | Code-1
136 | DCI | Civil | P4007-PM-RP-001 | Pre-Engineering Site Survey Report | A | 2 | COMPLETE | #VALUE! |  | 2018-02-16 | 137 | #N/A | Code-2
137 | DCI | Civil | P4007-PM-RP-002 | Geotechnical Survey Report | A | 1 | COMPLETE | #VALUE! |  | 2018-01-19 | 138 | #N/A | Code-1
138 | DCI | Civil | P4007-PM-RP-003 | Hydrogeological Report | A | Deleted | Rejected | #VALUE! |  | 2018-09-27 | 139 | #N/A | #N/A
139 | DCI | Civil | GCS-CVIN0001 | Drawing Index | I | 1 | COMPLETE | #VALUE! |  | 2018-01-16 | 140 | #N/A | Code-1
140 | DCI | Civil | GCS-CVTD0001 | Civil and Concrete Notes | I | 1 | COMPLETE | #VALUE! |  | 2018-01-16 | 141 | #N/A | Code-1
141 | DCI | Civil | GCS-CVTD0002 | Structural Steel Notes | I | 1 | COMPLETE | #VALUE! |  | 2018-01-16 | 142 | #N/A | Code-1
142 | DCI | Civil | GCS-CVTD0003 | Architectural Notes | I | 1 | COMPLETE | #VALUE! |  | 2018-01-16 | 143 | #N/A | Code-1
143 | DCI | Civil | GCS-CVTD0004 | Civil & Structural Legends | I | 1 | COMPLETE | #VALUE! |  | 2018-01-16 | 144 | #N/A | Code-1
144 | DCI | Civil | GCS-CVTD0005 | Architectural Legends | I | 1 | COMPLETE | #VALUE! |  | 2018-01-16 | 145 | #N/A | Code-1
145 | DCI | Civil | GCS-CVTD0006 | Standard Reinforcing Bar Details | I | 1 | COMPLETE | #VALUE! |  | 2018-01-16 | 146 | #N/A | Code-1
146 | DCI | Civil | GCS-CVTD0007 | Standard Anchor bolt Details | I | 1 | COMPLETE | #VALUE! |  | 2018-01-16 | 147 | #N/A | Code-1
147 | DCI | Civil | GCS-CVTD0008 | Standard Handrail Details | I | 1 | COMPLETE | #VALUE! |  | 2018-01-16 | 148 | #N/A | Code-1
148 | DCI | Civil | GCS-CVTD0009 | Standard Ladder Details | I | 1 | COMPLETE | #VALUE! |  | 2018-01-16 | 149 | #N/A | Code-1
149 | DCI | Civil | GCS-CVTD0010 | Standard steel Connection Details | I | Deleted | Rejected | #VALUE! |  | 2018-09-28 | 150 | #N/A | #N/A
150 | DCI | Civil | GCS-CVLY0001 | Overall Plot Plan | A | 2 | COMPLETE | #VALUE! |  | 2018-01-04 | 151 | #N/A | Code-2
151 | DCI | Civil | GCS-CVLY0002 | Pavement Details | A | 2 | COMPLETE | #VALUE! |  | 2018-04-17 | 152 | #N/A | Code-2
152 | DCI | Civil | GCS-CVLY0003 | Topography & Contour Survey Plan | A | 1 | COMPLETE | #VALUE! |  | 2018-01-05 | 153 | #N/A | Code-1
153 | DCI | Civil | GCS-CVLY0004 | Road Layout and Details | I | 1 | COMPLETE | #VALUE! |  | 2018-01-23 | 154 | #N/A | Code-1
154 | DCI | Civil | GCS-CVLY0005 | Storm Water Layout and Details | A | 3 | Rejected | #VALUE! | #VALUE! | 2018-03-01 | 155 | #N/A | Code-3
155 | DCI | Civil | GCS-CVLY0006 | Overall Foundation layout | I | 4 | Rejected | #VALUE! |  | 2018-10-31 | 156 | #N/A | Code-4
156 | DCI | Civil | GCS-CVLY0007 | Pipe rack -Structural steel Layout and details | I | 3 | Rejected | #VALUE! |  | 2018-09-25 | 157 | #N/A | Code-3
157 | DCI | Civil | GCS-CVLY0008 | Pipe rack -Foundation Layout and details | I | 3 | Rejected | #VALUE! |  | 2018-09-27 | 158 | #N/A | Code-3
158 | DCI | Civil | GCS-CVLY0010 | Electrical and Instrumentation Layout Trench and Details | I | Submitted | Rejected | #VALUE! |  | 2018-10-19 | 159 | #N/A | Submitted
159 | DCI | Civil | GCS-CVLY0012 | Misc. platforms foundation layout and details | I |  | Rejected | #VALUE! |  | 2018-10-19 | 160 | #N/A | NS
160 | DCI | Civil | GCS-CVLY0013 | Misc. platforms Structural layout and details | I | Submitted | Rejected | #VALUE! |  | 2018-10-19 | 161 | #N/A | Submitted
161 | DCI | Civil | GCS-CVLY0014 | Cable Tray & Duct Supports Structural layout and details | I | Deleted | Rejected | #VALUE! |  | 2018-10-19 | 162 | #N/A | #N/A
162 | DCI | Civil | GCS-CVLY0015 | Pipe supports foundation layout and details | I | 4 | Rejected | #VALUE! |  | 2018-10-19 | 163 | #N/A | Code-4
163 | DCI | Civil | GCS-CVLY0016 | Pipe supports Structural layout and details | I | 4 | Rejected | #VALUE! |  | 2018-10-19 | 164 | #N/A | Code-4
164 | DCI | Civil | GCS-CVLY0017 | Pipe Sleeper Foundation Layout, GA & RC details | I | 4 | Rejected | #VALUE! |  | 2018-10-19 | 165 | #N/A | Code-4
165 | DCI | Civil | GCS-CVDD0001 | GA & Architectural Details for Office Building & Control Room (Layout/Plan/Sectional Elevation ) | A | 2 | COMPLETE | #VALUE! |  | 2018-02-12 | 166 | #N/A | Code-2
166 | DCI | Civil | GCS-CVDD0002 | RCC Details for Office Building & Control Room (Foundation / Plinth / Grade Level / Lintel Level/ Roof Level) | A | 2 | COMPLETE | #VALUE! |  | 2018-02-14 | 167 | #N/A | Code-2
167 | DCI | Civil | GCS-CVDD0003 | GA & Architectural Details for Electrical Substation Room (Layout/Plan/Sectional Elevation ) | A | 1 | COMPLETE | #VALUE! |  | 2018-02-16 | 168 | #N/A | Code-1
168 | DCI | Civil | GCS-CVDD0004 | RCC Details for Electrical Substation Room (Foundation / Plinth / Grade Level / Lintel Level / Roof Level) | A | 1 | COMPLETE | #VALUE! |  | 2018-03-30 | 169 | #N/A | Code-1
169 | DCI | Civil | GCS-CVDD0005 | GA & Architectural Details for Security Room (Layout/Plan/Sectional Elevation ) | A | 1 | COMPLETE | #VALUE! |  | 2018-02-08 | 170 | #N/A | Code-1
170 | DCI | Civil | GCS-CVDD0006 | RCC Details for for Security Room (Foundation / Plinth/ Grade Level / Lintel Level / Roof Level) | A | 1 | COMPLETE | #VALUE! |  | 2018-02-21 | 171 | #N/A | Code-1
171 | DCI | Civil | GCS-CVDD0007 | GA & Architectural Details for Security Morcha (Layout/Plan/Sectional Elevation ) | A | 1 | COMPLETE | #VALUE! |  | 2018-02-08 | 172 | #N/A | Code-1
172 | DCI | Civil | GCS-CVDD0008 | RCC Details for for Security Morcha (Foundation / Plinth / Grade Level / Lintel Level / Roof Level) | A | 1 | COMPLETE | #VALUE! |  | 2018-02-21 | 173 | #N/A | Code-1
173 | DCI | Civil | GCS-CVDD0009 | GA & Architectural Details for Watch Tower (Layout/Plan/Sectional Elevation ) | A | 1 | COMPLETE | #VALUE! |  | 2018-01-22 | 174 | #N/A | Code-1
174 | DCI | Civil | GCS-CVDD0010 | RCC Details for Watch Tower (Foundation / Plinth / Grade Level / Lintel Level / Roof Level) | A | 1 | COMPLETE | #VALUE! |  | 2018-01-24 | 175 | #N/A | Code-1
175 | DCI | Civil | GCS-CVDD0011 | GA Details for Generator Room (Layout/Plan/Sectional Elevation ) | A | 3 | Rejected | #VALUE! |  | 2018-09-28 | 176 | #N/A | Code-3
176 | DCI | Civil | GCS-CVDD0012 | RCC Details for Generator Room (Foundation / Plinth / Grade Level / Lintel Level / Roof Level) | A | 3 | Rejected | #VALUE! |  | 2018-09-28 | 177 | #N/A | Code-3
177 | DCI | Civil | GCS-CVDD0013 | GA Drawing for Fire Water Pump Shed (Layout/Plan/Sectional Elevation) | A |  | Rejected | #VALUE! |  | 2018-09-28 | 178 | #N/A | NS
178 | DCI | Civil | GCS-CVDD0014 | RCC Details for Fire Water Pump Shed (Foundation / Plinth / Grade Level) | A | Submitted | Rejected | #VALUE! |  | 2018-09-28 | 179 | #N/A | Submitted
179 | DCI | Civil | GCS-CVDD0016 | GA Drawing for Gas Lift Compressor Shed (Layout/Plan/Sectional Elevation) | A |  | Rejected | #VALUE! |  | 2018-09-28 | 180 | #N/A | NS
180 | DCI | Civil | GCS-CVDD0017 | RCC Details for Gas Lift Compressor Shed (Foundation / Plinth / Grade Level) | A |  | Rejected | #VALUE! |  | 2018-09-28 | 181 | #N/A | NS
181 | DCI | Civil | GCS-CVDD0019 | GA Drawing for Vehicle Parking Shed (Layout/Plan/Sectional Elevation) | A | 1 | COMPLETE | #VALUE! |  | 2018-03-19 | 182 | #N/A | Code-1
182 | DCI | Civil | GCS-CVDD0020 | RCC Details for Vehicle Parking Shed (Foundation / Plinth / Grade Level) | A | 1 | COMPLETE | #VALUE! |  | 2018-03-19 | 183 | #N/A | Code-1
183 | DCI | Civil | GCS-CVDD0021 | Structural Steel Detail for Vehicle Parking Shed | A | 2 | COMPLETE | #VALUE! |  | 2018-03-19 | 184 | #N/A | Code-2
184 | DCI | Civil | GCS-CVDD0022 | Foundation Details for Effluent Water Transfer Pums - 5002 A/B | A | Submitted | Rejected | #VALUE! |  | 2018-10-31 | 185 | #N/A | Submitted
185 | DCI | Civil | GCS-CVDD0023 | Foundation Details for Effluent Water Disposal Pumps - P3011 A/B | A | Submitted | Rejected | #VALUE! |  | 2018-10-31 | 186 | #N/A | Submitted
186 | DCI | Civil | GCS-CVDD0025 | GA & RCC Details for Effluent Water Storage Tank - T3010 | A | Submitted | Rejected | #VALUE! |  | 2018-10-31 | 187 | #N/A | Submitted
187 | DCI | Civil | GCS-CVDD0026 | GA & RCC Details for Closed Blow Down Condensate Storage Vessel - V5001 | A | Submitted | Rejected | #VALUE! |  | 2018-10-31 | 188 | #N/A | Submitted
188 | DCI | Civil | GCS-CVDD0027 | Foundation details for Lighting pole and High mast | A | Submitted | Rejected | #VALUE! |  | 2018-10-31 | 189 | #N/A | Submitted
189 | DCI | Civil | GCS-CVDD0028 | RCC Details for Raw Water Storage Tank - T4501 | A | 1 | COMPLETE | #VALUE! |  | 2018-04-23 | 190 | #N/A | Code-1
190 | DCI | Civil | GCS-CVDD0029 | GA & Sectional Details for Tube well (Layout/Plan/Sectional Elevation ) | A | 1 | COMPLETE | #VALUE! |  | 2018-02-06 | 191 | #N/A | Code-1
191 | DCI | Civil | GCS-CVDD0030 | RCC Details for Tube well (Foundation / Plinth / Grade Level / Lintel Level / Roof Level) | I | 1 | COMPLETE | #VALUE! |  | 2018-02-06 | 192 | #N/A | Code-1
192 | DCI | Civil | GCS-CVDD0031 | GA drawing for Lp Gas Compressor Shed (Layout/Plan/Sectional Elevation) | A |  | Rejected | #VALUE! |  | 2018-10-31 | 193 | #N/A | NS
193 | DCI | Civil | GCS-CVDD0032 | Typical Details Of Temporary Barricade | A | Deleted | Rejected | #VALUE! |  | 2018-11-30 | 194 | #N/A | #N/A
194 | DCI | Civil | GCS-CVDD0033 | RCC Details for Lp Gas Compressor Shed (Foundation / Plinth / Grade Level) | I |  | Rejected | #VALUE! |  | 2018-10-31 | 195 | #N/A | NS
195 | DCI | Civil | GCS-CVDD0035 | GA & Sectional Details for Maintenance Building | A | 1 | COMPLETE | #VALUE! |  | 2018-03-20 | 196 | #N/A | Code-1
196 | DCI | Civil | GCS-CVDD0036 | RCC Details for for Maintenance Building | I | 1 | COMPLETE | #VALUE! |  | 2018-03-20 | 197 | #N/A | Code-1
197 | DCI | Civil | GCS-CVDD0037 | Equipment Foundation Details V-6501 | I | Submitted | Rejected | #VALUE! |  | 2018-10-31 | 198 | #N/A | Submitted
198 | DCI | Civil | GCS-CVDD0038 | GA & RCC Details of LP Gas Knock-Out Drum V-1001 A/B & V-1002 | I | 1 | COMPLETE | #VALUE! |  | 2018-10-31 | 199 | #N/A | Code-1
199 | DCI | Civil | GCS-CVDD0039 | Equipment Foundation Details V-1002 | I | Deleted | Rejected | #VALUE! |  | 2018-10-31 | 200 | #N/A | #N/A
200 | DCI | Civil | GCS-CVDD0040 | GA & RCC Details of MP Gas Knock-Out Drum V-1501 A/B & V-1502 | I | 1 | COMPLETE | #VALUE! |  | 2018-10-31 | 201 | #N/A | Code-1
201 | DCI | Civil | GCS-CVDD0041 | Equipment Foundation Details V-1502 | I | Deleted | Rejected | #VALUE! |  | 2018-10-31 | 202 | #N/A | #N/A
202 | DCI | Civil | GCS-CVDD0042 | GA & RCC Details of HP Gas Knock-Out Drum V-2001 A/B | I | 1 | COMPLETE | #VALUE! |  | 2018-10-31 | 203 | #N/A | Code-1
203 | DCI | Civil | GCS-CVDD0044 | Equipment Foundation Details T-4502 | I | 1 | COMPLETE | #VALUE! |  | 2018-04-09 | 204 | #N/A | Code-1
204 | DCI | Civil | GCS-CVDD0045 | Equipment Foundation Details T-4503 | I | Submitted | Rejected | #VALUE! |  | 2018-10-31 | 205 | #N/A | Submitted
205 | DCI | Civil | GCS-CVDD0047 | Equipment Foundation Details T-5001 | I | Submitted | Rejected | #VALUE! |  | 2018-10-31 | 206 | #N/A | Submitted
206 | DCI | Civil | GCS-CVDD0048 | Equipment Foundation Details T-5002 | I | 3 | Rejected | #VALUE! | #VALUE! | 2018-04-23 | 207 | #N/A | Code-3
207 | DCI | Civil | GCS-CVDD0049 | Equipment Foundation Details T-6001 | I | 2 | COMPLETE | #VALUE! |  | 2018-04-23 | 208 | #N/A | Code-2
208 | DCI | Civil | GCS-CVDD0050 | Equipment Foundation Details A-1001 A/B/C | I |  | Rejected | #VALUE! |  | 2018-10-31 | 209 | #N/A | NS
209 | DCI | Civil | GCS-CVDD0051 | Equipment Foundation Details A-2001 A/B/C | I |  | Rejected | #VALUE! |  | 2018-10-31 | 210 | #N/A | NS
210 | DCI | Civil | GCS-CVDD0052 | Equipment Foundation Details A-1501 | I | 4 | Rejected | #VALUE! |  | 2018-10-31 | 211 | #N/A | Code-4
211 | DCI | Civil | GCS-CVDD0053 | Equipment Foundation Details A-2501 | I | Submitted | Rejected | #VALUE! |  | 2018-10-31 | 212 | #N/A | Submitted
212 | DCI | Civil | GCS-CVDD0054 | Equipment Foundation Details A-3001 | I |  | Rejected | #VALUE! |  | 2018-10-31 | 213 | #N/A | NS
213 | DCI | Civil | GCS-CVDD0055 | Equipment Foundation Details A-3501 | I |  | Rejected | #VALUE! |  | 2018-10-31 | 214 | #N/A | NS
214 | DCI | Civil | GCS-CVDD0056 | Equipment Foundation Details A-4001 A/B | I | 4 | Rejected | #VALUE! |  | 2018-10-31 | 215 | #N/A | Code-4
215 | DCI | Civil | GCS-CVDD0057 | Equipment Foundation Details A-4501 | I |  | Rejected | #VALUE! |  | 2018-10-31 | 216 | #N/A | NS
216 | DCI | Civil | GCS-CVDD0058 | Equipment Foundation Details A-4502 A/B | I | Deleted | Rejected | #VALUE! |  | 2018-10-12 | 217 | #N/A | #N/A
217 | DCI | Civil | GCS-CVDD0059 | Equipment Foundation Details A-5501 | I | Submitted | Rejected | #VALUE! |  | 2018-10-31 | 218 | #N/A | Submitted
218 | DCI | Civil | GCS-CVDD0060 | Equipment Foundation Details A-8001 | I |  | Rejected | #VALUE! |  | 2018-10-31 | 219 | #N/A | NS
219 | DCI | Civil | GCS-CVDD0061 | Equipment Foundation Details P-4502 A/B | I |  | Rejected | #VALUE! |  | 2018-10-31 | 220 | #N/A | NS
220 | DCI | Civil | GCS-CVDD0062 | Equipment Foundation Details P-4503 A/B | I | Submitted | Rejected | #VALUE! |  | 2018-10-31 | 221 | #N/A | Submitted
221 | DCI | Civil | GCS-CVDD0063 | Equipment Foundation Details P-5001 A/B | I | Deleted | Rejected | #VALUE! |  | 2018-10-12 | 222 | #N/A | #N/A
222 | DCI | Civil | GCS-CVDD0064 | Equipment Foundation Details P-5003 | I | Submitted | Rejected | #VALUE! |  | 2018-10-12 | 223 | #N/A | Submitted
223 | DCI | Civil | GCS-CVDD0065 | Equipment Foundation Details P-5004 | I | Deleted | Rejected | #VALUE! |  | 2018-10-12 | 224 | #N/A | #N/A
224 | DCI | Civil | GCS-CVDD0067 | Equipment Foundation Details P-6001 A/B | I | Submitted | Rejected | #VALUE! |  | 2018-10-31 | 225 | #N/A | Submitted
225 | DCI | Civil | GCS-CVDD0068 | Equipment Foundation Details P-6002 A/B | I | Submitted | Rejected | #VALUE! |  | 2018-10-31 | 226 | #N/A | Submitted
226 | DCI | Civil | GCS-CVDD0069 | Equipment Foundation Details P-6501 A/B | I |  | Rejected | #VALUE! |  | 2018-10-31 | 227 | #N/A | NS
227 | DCI | Civil | GCS-CVDD0070 | Storm water reservoir water system -Rcc Tank GA&Rc details | I | Submitted | Rejected | #VALUE! |  | 2018-10-31 | 228 | #N/A | Submitted
228 | DCI | Civil | GCS-CVDD0071 | Valve pits GA&RC details | I | Submitted | Rejected | #VALUE! |  | 2018-10-31 | 229 | #N/A | Submitted
229 | DCI | Civil | GCS-CVDD0073 | Potable water and sewer pits GA&RC details | A | 4 | Rejected | #VALUE! |  | 2018-10-31 | 230 | #N/A | Code-4
230 | DCI | Civil | GCS-CVDD0074 | oily water sewer pits GA&RC details | A | Submitted | Rejected | #VALUE! |  | 2018-10-31 | 231 | #N/A | Submitted
231 | DCI | Civil | GCS-CVDD0075 | Man holes and catch basins pits GA&RC details | I |  | Rejected | #VALUE! |  | 2018-10-31 | 232 | #N/A | NS
232 | DCI | Civil | GCS-CVDD0076 | soak pit and septic tank pits GA& details | I | 1 | COMPLETE | #VALUE! |  | 2018-05-14 | 233 | #N/A | Code-1
233 | DCI | Civil | GCS-CVDD0078 | ERC /IRC duct bank GA& details | I | 4 | Rejected | #VALUE! |  | 2018-10-31 | 234 | #N/A | Code-4
234 | DCI | Civil | GCS-CVDD0079 | Under Ground Composite Layout | I |  | Rejected | #VALUE! |  | 2018-10-31 | 235 | #N/A | NS
235 | DCI | Civil | GCS-CVDD0080 | Microwave tower foundation _GA details | I |  | Rejected | #VALUE! |  | 2018-10-31 | 236 | #N/A | NS
236 | DCI | Civil | GCS-CVDD0081 | Foundation details for misc. electrical and instrument panels | I | Deleted | Rejected | #VALUE! |  | 2018-10-31 | 237 | #N/A | #N/A
237 | DCI | Civil | GCS-CVDD0082 | Cable Tray & Duct Supports Foundation and details | I | Deleted | Rejected | #VALUE! |  | 2018-10-31 | 238 | #N/A | #N/A
238 | DCI | Civil | GCS-CVDD0083 | RCC Details for Nitrogen Generation & Air System Shed (Foundation / plinth/ Grade Level) | A | 3 | Rejected | #VALUE! |  | 2018-10-31 | 239 | #N/A | Code-3
239 | DCI | Civil | GCS-CVDD0084 | GA Drawing for Nitrogen Generation & Air System Shed (Layout /plan /Sectional Elevation) | A | Deleted | Rejected | #VALUE! |  | 2018-10-31 | 240 | #N/A | #N/A
240 | DCI | Civil | GCS-CVDD0085 | GA & Structural details for Utility Air system shed |  | 3 | [5 empty] | #N/A | Code-3
241 | DCI | Civil | GCS-CVDD0086 | RCC Details for Glycol Regen. Skid shed (Foundation / plinth/ Grade Level) | A |  | Rejected | #VALUE! |  | 2018-10-31 | 241 | #N/A | NS
242 | DCI | Civil | GCS-CVDD0087 | GA Drawing for Glycol Regen. Shed (Layout /plan /Sectional Elevation) | A | Deleted | Rejected | #VALUE! |  | 2018-10-31 | 242 | #N/A | #N/A
243 | DCI | Civil | GCS-CVDD0089 | RCC Details for Clean Agent Shed (Foundation / Grade Level) | A | 1 | COMPLETE | #VALUE! |  | 2018-09-14 | 243 | #N/A | Code-1
244 | DCI | Civil | GCS-CVDD0090 | GA & Structural details for Clean agent Shed (Layout /plan /Sectional Elevation) | A | 1 | COMPLETE | #VALUE! |  | 2018-07-11 | 244 | #N/A | Code-1
245 | DCI | Civil | GCS-CVDD0091 | GA & Steel Details for Generator Room Shed (Layout/Plan/Sectional Elevation) | A | Deleted | Rejected | #VALUE! |  | 2018-10-31 | 245 | #N/A | #N/A
246 | DCI | Civil | GCS-CVDD0092 |  |  | 1 | [5 empty] | #N/A | Code-1
247 | DCI | Civil | GCS-CVDD0093 | [8 empty] | #N/A | NS
248 | DCI | Civil | P4007-CV-RP-001 | Design Calculations for Office Building & Control Room (RCC Super Structure / Foundation) | A | 2 | COMPLETE | #VALUE! |  | 2018-02-14 | 246 | #N/A | Code-2
249 | DCI | Civil | P4007-CV-RP-002 | Design Calculations for Electrical Substation Room (RCC Super Structure / Foundation) | A | 1 | COMPLETE | #VALUE! |  | 2018-02-23 | 247 | #N/A | Code-1
250 | DCI | Civil | P4007-CV-RP-003 | Design Calculations for Security Room (RCC Super Structure / Foundation) | A | 1 | COMPLETE | #VALUE! |  | 2018-02-21 | 248 | #N/A | Code-1
251 | DCI | Civil | P4007-CV-RP-004 | Design Calculations for Security Morcha (RCC Super Structure / Foundation) | A | 1 | COMPLETE | #VALUE! |  | 2018-02-21 | 249 | #N/A | Code-1
252 | DCI | Civil | P4007-CV-RP-005 | Design Calculations for Watch Tower (RCC Super Structure / Foundation) | A | 1 | COMPLETE | #VALUE! |  | 2018-01-25 | 250 | #N/A | Code-1
253 | DCI | Civil | P4007-CV-RP-006 | Design Calculations for Generator Room (RCC Super Structure / Foundation) | A | 3 | Rejected | #VALUE! |  | 2018-10-12 | 251 | #N/A | Code-3
254 | DCI | Civil | P4007-CV-RP-007 | Design Calculations for Fire Water Pump Shed (Structural / Foundation) | A |  | Rejected | #VALUE! |  | 2018-10-12 | 252 | #N/A | NS
255 | DCI | Civil | P4007-CV-RP-008 | Design Calculations for Gas Compressor Shed (Structural / Foundation) | A |  | Rejected | #VALUE! |  | 2018-10-12 | 253 | #N/A | NS
256 | DCI | Civil | P4007-CV-RP-009 | Design Calculations for Vehicle Parking Shed (Structural / Foundation) | A | 2 | COMPLETE | #VALUE! |  | 2018-03-19 | 254 | #N/A | Code-2
257 | DCI | Civil | P4007-CV-RP-010 | Foundation Design calculation for Effluent Water Transfer Pumps | A | Deleted | Rejected | #VALUE! |  | 2018-10-26 | 255 | #N/A | #N/A
258 | DCI | Civil | P4007-CV-RP-011 | Foundation Design calculation for Effluent Water Disposal Pumps | A | Submitted | Rejected | #VALUE! |  | 2018-10-26 | 256 | #N/A | Submitted
259 | DCI | Civil | P4007-CV-RP-013 | Foundation & RCC Design Calculation for Effluent Water Storage Tank | A | Submitted | Rejected | #VALUE! |  | 2018-10-26 | 257 | #N/A | Submitted
260 | DCI | Civil | P4007-CV-RP-014 | Foundation & RCC Design Calculation for Closed Blow Down Condensate Storage Tank | A | Deleted | Rejected | #VALUE! |  | 2018-10-26 | 258 | #N/A | #N/A
261 | DCI | Civil | P4007-CV-RP-015 | Foundation Design calculation for Lighting pole and High mast | A | Submitted | Rejected | #VALUE! |  | 2018-10-26 | 259 | #N/A | Submitted
262 | DCI | Civil | P4007-CV-RP-016 | Equipment Foundation Report Details V-6501 | A | Submitted | Rejected | #VALUE! |  | 2018-10-31 | 260 | #N/A | Submitted
263 | DCI | Civil | P4007-CV-RP-017 | Equipment Foundation Report Details V-1001 A/B | A | 1 | COMPLETE | #VALUE! |  | 2018-10-31 | 261 | #N/A | Code-1
264 | DCI | Civil | P4007-CV-RP-018 | Equipment Foundation Report Details V-1002 | A | Deleted | Rejected | #VALUE! |  | 2018-10-31 | 262 | #N/A | #N/A
265 | DCI | Civil | P4007-CV-RP-019 | Equipment Foundation Report Details V-1501 A/B | A | 1 | COMPLETE | #VALUE! |  | 2018-10-31 | 263 | #N/A | Code-1
266 | DCI | Civil | P4007-CV-RP-020 | Equipment Foundation Report Details V-1502 | A | Deleted | Rejected | #VALUE! |  | 2018-10-31 | 264 | #N/A | #N/A
267 | DCI | Civil | P4007-CV-RP-021 | Equipment Foundation Report Details V-2001 A/B | A | 1 | COMPLETE | #VALUE! |  | 2018-10-31 | 265 | #N/A | Code-1
268 | DCI | Civil | P4007-CV-RP-023 | Equipment Foundation Report Details T-4502 | A | 1 | COMPLETE | #VALUE! |  | 2018-04-09 | 266 | #N/A | Code-1
269 | DCI | Civil | P4007-CV-RP-024 | Equipment Foundation Report Details T-4503 | A | Submitted | Rejected | #VALUE! |  | 2018-10-31 | 267 | #N/A | Submitted
270 | DCI | Civil | P4007-CV-RP-026 | Equipment Foundation Report Details T-5001 | A | Submitted | Rejected | #VALUE! |  | 2018-10-31 | 268 | #N/A | Submitted
271 | DCI | Civil | P4007-CV-RP-027 | Equipment Foundation Report Details T-5002 | A | 3 | Rejected | #VALUE! | #VALUE! | 2018-04-23 | 269 | #N/A | Code-3
272 | DCI | Civil | P4007-CV-RP-028 | Equipment Foundation Report Details T-6001 | A | 1 | COMPLETE | #VALUE! |  | 2018-04-23 | 270 | #N/A | Code-1
273 | DCI | Civil | P4007-CV-RP-029 | Equipment Foundation Report Details A-1001 A/B/C | A |  | Rejected | #VALUE! |  | 2018-10-01 | 271 | #N/A | NS
274 | DCI | Civil | P4007-CV-RP-030 | Equipment Foundation Report Details A-2001 A/B/C | A |  | Rejected | #VALUE! |  | 2018-10-01 | 272 | #N/A | NS
275 | DCI | Civil | P4007-CV-RP-031 | Equipment Foundation Report Details A-1501 | A | Submitted | Rejected | #VALUE! |  | 2018-10-01 | 273 | #N/A | Submitted
276 | DCI | Civil | P4007-CV-RP-032 | Equipment Foundation Report Details A-2501 | A | Submitted | Rejected | #VALUE! |  | 2018-10-01 | 274 | #N/A | Submitted
277 | DCI | Civil | P4007-CV-RP-033 | Equipment Foundation Report Details A-3001 | A |  | Rejected | #VALUE! |  | 2018-10-05 | 275 | #N/A | NS
278 | DCI | Civil | P4007-CV-RP-034 | Equipment Foundation Report Details A-3501 | A |  | Rejected | #VALUE! |  | 2018-10-05 | 276 | #N/A | NS
279 | DCI | Civil | P4007-CV-RP-035 | Equipment Foundation Report Details A-4001 A/B | A | 2 | COMPLETE | #VALUE! |  | 2018-10-05 | 277 | #N/A | Code-2
280 | DCI | Civil | P4007-CV-RP-036 | Equipment Foundation Report Details A-4501 | A |  | Rejected | #VALUE! |  | 2018-10-05 | 278 | #N/A | NS
281 | DCI | Civil | P4007-CV-RP-037 | Equipment Foundation Report Details A-4502 A/B | A | Deleted | Rejected | #VALUE! |  | 2018-10-12 | 279 | #N/A | #N/A
282 | DCI | Civil | P4007-CV-RP-038 | Equipment Foundation Report Details A-5501 | A | Submitted | Rejected | #VALUE! |  | 2018-10-05 | 280 | #N/A | Submitted
283 | DCI | Civil | P4007-CV-RP-039 | Equipment Foundation Report Details A-8001 | A |  | Rejected | #VALUE! |  | 2018-10-05 | 281 | #N/A | NS
284 | DCI | Civil | P4007-CV-RP-040 | Equipment Foundation Report Details P-4502 A/B | A |  | Rejected | #VALUE! |  | 2018-10-05 | 282 | #N/A | NS
285 | DCI | Civil | P4007-CV-RP-041 | Equipment Foundation Report Details P-4503 A/B | A | Submitted | Rejected | #VALUE! |  | 2018-10-05 | 283 | #N/A | Submitted
286 | DCI | Civil | P4007-CV-RP-042 | Equipment Foundation Report Details P-5001 A/B | A | Submitted | Rejected | #VALUE! |  | 2018-10-12 | 284 | #N/A | Submitted
287 | DCI | Civil | P4007-CV-RP-043 | Equipment Foundation Report Details P-5003 | A | Submitted | Rejected | #VALUE! |  | 2018-10-12 | 285 | #N/A | Submitted
288 | DCI | Civil | P4007-CV-RP-044 | Equipment Foundation Report Details P-5004 | A | Submitted | Rejected | #VALUE! |  | 2018-10-12 | 286 | #N/A | Submitted
289 | DCI | Civil | P4007-CV-RP-046 | Equipment Foundation Report Details P-6001 A/B | A | Submitted | Rejected | #VALUE! |  | 2018-10-05 | 287 | #N/A | Submitted
290 | DCI | Civil | P4007-CV-RP-047 | Equipment Foundation Report Details P-6002 A/B | A | Submitted | Rejected | #VALUE! |  | 2018-10-05 | 288 | #N/A | Submitted
291 | DCI | Civil | P4007-CV-RP-048 | Equipment Foundation Report Details P-6501 A/B | A |  | Rejected | #VALUE! |  | 2018-10-05 | 289 | #N/A | NS
292 | DCI | Civil | P4007-CV-RP-049 | Pipe rack -Structural analysis and design Report | A | 3 | Rejected | #VALUE! |  | 2018-09-28 | 290 | #N/A | Code-3
293 | DCI | Civil | P4007-CV-RP-050 | Maintenance Building -Structural analysis and design Report | A | 1 | COMPLETE | #VALUE! |  | 2018-05-01 | 291 | #N/A | Code-1
294 | DCI | Civil | P4007-CV-RP-051 | Tubewell Room -Structural analysis and design Report | A | 1 | COMPLETE | #VALUE! |  | 2018-05-01 | 292 | #N/A | Code-1
295 | DCI | Civil | P4007-CV-RP-052 | Pipe Sleepers -Structural analysis and design Report | A | Submitted | Rejected | #VALUE! |  | 2018-10-31 | 293 | #N/A | Submitted
296 | DCI | Civil | P4007-CV-RP-053 | Design Calculation of Glycol Regen Skid Shed | A |  | Rejected | #VALUE! |  | 2018-10-31 | 294 | #N/A | NS
297 | DCI | Civil | P4007-CV-RP-054 | Design Calculation of Nitrogen Generation & Air Syatem Shed | A | 1 | COMPLETE | #VALUE! |  | 2018-10-31 | 295 | #N/A | Code-1
298 | DCI | Civil | P4007-CV-RP-055 | Design Calculation of Concrete Road | A | 1 | COMPLETE | #VALUE! |  | 2018-05-12 | 296 | #N/A | Code-1
299 | DCI | Civil | P4007-CV-RP-056 | Storm water Drain Calculation | A | 2 | COMPLETE | #VALUE! |  | 2018-07-01 | 297 | #N/A | Code-2
300 | DCI | Civil | P4007-CV-RP-057 | Storage Tank-4501 | A | 1 | COMPLETE | #VALUE! |  | 2018-04-19 | 298 | #N/A | Code-1
301 | DCI | Civil | P4007-CV-RP-058 | Calculation report for Clean agent Shed and foundations | A | 1 | COMPLETE | #VALUE! |  | 2018-09-14 | 299 | #N/A | Code-1
302 | DCI | Civil | P4007-CV-RP-059 | Calculation Report for Inert Gas Generation Package A-3502 | A | 1 | COMPLETE | #VALUE! |  | 2018-10-31 | 300 | #N/A | Code-1
303 | DCI | Civil | P4007-CV-RP-060 | Calculation Report for Diesel Day Tank T-6002 A/B/C | A |  | Rejected | #VALUE! |  | 2018-10-31 | 301 | #N/A | NS
304 | DCI | Civil | P4007-CV-RP-061 | Design Calculations for LP Compressor Shed | A |  | Rejected | #VALUE! |  | 2018-10-31 | 302 | #N/A | NS
305 | DCI | Electrical | P4007-EL-DB-001 | Electrical Design Basis | A | 1 | COMPLETE | #VALUE! |  | 2017-12-01 | 303 | #N/A | Code-1
306 | DCI | Electrical | P4007-EL-DS-001 | Datasheet for Gas Enginer Alternator | A | 1 | COMPLETE | #VALUE! |  | 2018-01-09 | 304 | #N/A | Code-1
307 | DCI | Electrical | P4007-EL-DS-002 | Datasheet for Diesel Engine Alternator | A | 1 | COMPLETE | #VALUE! | #VALUE! | 2018-01-12 | 305 | #N/A | Code-1
308 | DCI | Electrical | P4007-EL-DS-003 | Datasheet for LV Switchgear / MCC & Bus Duct | A | 1 | COMPLETE | #VALUE! |  | 2018-01-19 | 306 | #N/A | Code-1
309 | DCI | Electrical | P4007-EL-DS-004 | Typical Datasheet for LV Motor | A | 1 | COMPLETE | #VALUE! |  | 2017-12-29 | 307 | #N/A | Code-1
310 | DCI | Electrical | P4007-EL-DS-005 | Datasheet for AC UPS & DB | A | 1 | COMPLETE | #VALUE! |  | 2018-01-25 | 308 | #N/A | Code-1
311 | DCI | Electrical | P4007-EL-DS-006 | Datasheet for Battery Charger & DB | A | 1 | COMPLETE | #VALUE! |  | 2018-01-25 | 309 | #N/A | Code-1
312 | DCI | Electrical | P4007-EL-DS-007 | Datasheet for LV Distribution Board | A | Submitted | Rejected | #VALUE! |  | 2018-09-27 | 310 | #N/A | Submitted
313 | DCI | Electrical | P4007-EL-DS-008 | Datasheet for Lighting Transformer | A | 1 | COMPLETE | #VALUE! |  | 2018-02-02 | 311 | #N/A | Code-1
314 | DCI | Electrical | P4007-EL-DS-009 | Datasheet for NGR | A | 1 | COMPLETE | #VALUE! |  | 2018-01-12 | 312 | #N/A | Code-1
315 | DCI | Electrical | P4007-EL-DS-010 | Datasheet for LPBS | A | 1 | COMPLETE | #VALUE! |  | 2018-03-15 | 313 | #N/A | Code-1
316 | DCI | Electrical | P4007-EL-DS-011 | Datasheet for Power & Control Cables | A | 1 | COMPLETE | #VALUE! |  | 2018-03-22 | 314 | #N/A | Code-1
317 | DCI | Electrical | P4007-EL-RP-001 | Electrical Load List | A | 2 | COMPLETE | #VALUE! |  | 2018-01-10 | 315 | #N/A | Code-2
318 | DCI | Electrical | P4007-EL-RP-002 | Generator Sizing calculation | A | 1 | COMPLETE | #VALUE! |  | 2018-01-17 | 316 | #N/A | Code-1
319 | DCI | Electrical | P4007-EL-RP-003 | NGR Sizing calculation | A | 1 | COMPLETE | #VALUE! |  | 2018-01-25 | 317 | #N/A | Code-1
320 | DCI | Electrical | P4007-EL-RP-004 | Ligiting Transformer Sizing calculation | A | 1 | COMPLETE | #VALUE! |  | 2018-03-16 | 318 | #N/A | Code-1
321 | DCI | Electrical | P4007-EL-RP-005 | Earthing & Lightning Design Calculation | A | 3 | Rejected | #VALUE! | #VALUE! | 2018-02-09 | 319 | #N/A | Code-3
322 | DCI | Electrical | P4007-EL-RP-006 | Electrical AC UPS Sizing calculation | A | 1 | COMPLETE | #VALUE! |  | 2018-01-19 | 320 | #N/A | Code-1
323 | DCI | Electrical | P4007-EL-RP-007 | Electrical DC Battery Charger Sizing calculation | A | 1 | COMPLETE | #VALUE! |  | 2018-01-19 | 321 | #N/A | Code-1
324 | DCI | Electrical | P4007-EL-RP-008 | Electrical Cable Sizing Calculation | A | 1 | COMPLETE | #VALUE! |  | 2018-02-23 | 322 | #N/A | Code-1
325 | DCI | Electrical | P4007-EL-RP-009 | Electrical System Study (Load flow, Short circuit & Motor Starting study) | I | Submitted | Rejected | #VALUE! |  | 2018-09-26 | 323 | #N/A | Submitted
326 | DCI | Electrical | P4007-EL-RP-010 | Lighting Design Calculation | I | 1 | COMPLETE | #VALUE! |  | 2018-03-09 | 324 | #N/A | Code-1
327 | DCI | Electrical | P4007-EL-RP-011 | Relay Setting & Co-ordination | I |  | Rejected | #VALUE! |  | 2018-10-10 | 325 | #N/A | NS
328 | DCI | Electrical | P4007-EL-SC-001 | Electrical Cable Schedule | A | Submitted | Rejected | #VALUE! |  | 2018-09-27 | 326 | #N/A | Submitted
329 | DCI | Electrical | P4007-EL-SP-001 | Electrical Generator operating Philosophy | A | 1 | COMPLETE | #VALUE! |  | 2018-05-16 | 327 | #N/A | Code-1
330 | DCI | Electrical | GCS-ELIC0001 | Electrical Interconnection Wiring Diagrams (Cable Termination) | A |  | Rejected | #VALUE! |  | 2018-10-26 | 328 | #N/A | NS
331 | DCI | Electrical | GCS-ELID0001 | Typical Electrical Installation Drawing - Cable Ladder & Trench | A | 1 | COMPLETE | #VALUE! |  | 2018-01-25 | 329 | #N/A | Code-1
332 | DCI | Electrical | GCS-ELID0002 | Typical Electrical Installation Drawing - Earthing & Lightning | A | 1 | COMPLETE | #VALUE! |  | 2018-01-25 | 330 | #N/A | Code-1
333 | DCI | Electrical | GCS-ELID0003 | Typical Electrical Installation Drawing - Lighting | A | 3 | Rejected | #VALUE! | #VALUE! | 2018-01-25 | 331 | #N/A | Code-3
334 | DCI | Electrical | GCS-ELLY0001 | Electrical Equipment Room Layout | A | 3 | Rejected | #VALUE! |  | 2018-10-10 | 332 | #N/A | Code-3
335 | DCI | Electrical | GCS-ELLY0002 | Earthing & Lightning Protection Layout | A | 3 | Rejected | #VALUE! |  | 2018-09-27 | 333 | #N/A | Code-3
336 | DCI | Electrical | GCS-ELLY0003 | Overall Cable Layout | A | Submitted | Rejected | #VALUE! |  | 2018-09-27 | 334 | #N/A | Submitted
337 | DCI | Electrical | GCS-ELLY0004 | Plant Cable Layout | A | Deleted | Rejected | #VALUE! |  | 2018-09-27 | 335 | #N/A | #N/A
338 | DCI | Electrical | GCS-ELSD0001 | Key Single Line Diagram | A | 1 | COMPLETE | #VALUE! |  | 2018-01-19 | 336 | #N/A | Code-1
339 | DCI | Electrical | GCS-ELSD0002 | Electrical Single Line Diagram for PCC | A | 1 | COMPLETE | #VALUE! |  | 2018-02-09 | 337 | #N/A | Code-1
340 | DCI | Electrical | GCS-ELSD0003 | Electrical Single Line Diagram for MCC | A | 1 | COMPLETE | #VALUE! |  | 2018-02-09 | 338 | #N/A | Code-1
341 | DCI | Electrical | GCS-ELSD0004 | Electrical Single Line Diagram for AC UPS DB | A | 1 | COMPLETE | #VALUE! |  | 2018-02-23 | 339 | #N/A | Code-1
342 | DCI | Electrical | GCS-ELSD0005 | Electrical Single Line Diagram for DC Battery Charger DB | A | 1 | COMPLETE | #VALUE! |  | 2018-02-23 | 340 | #N/A | Code-1
343 | DCI | Electrical | GCS-ELSD0006 | Electrical Single Line Diagram for MPDB | A | 1 | COMPLETE | #VALUE! | #VALUE! | 2018-03-09 | 341 | #N/A | Code-1
344 | DCI | Electrical | GCS-ELSD0007 | Electrical Single Line Diagram for Lighting DB's | A | 1 | COMPLETE | #VALUE! | #VALUE! | 2018-03-09 | 342 | #N/A | Code-1
345 | DCI | Electrical | GCS-ELSD0008 | Electrical Single Line Diagram for PDB | A | 1 | COMPLETE | #VALUE! |  | 2018-10-10 | 343 | #N/A | Code-1
346 | DCI | Electrical | GCS-ELSD0009 | Electrical Single Line Diagram for MELDB | A | Submitted | Rejected | #VALUE! |  | 2018-10-10 | 344 | #N/A | Submitted
347 | DCI | Electrical | GCS-ELSD0010 | Electrical Single Line Diagram for NLDB-7001 | A | Submitted | Rejected | #VALUE! |  | 2018-10-10 | 345 | #N/A | Submitted
348 | DCI | Electrical | GCS-ELSD0011 | Electrical Single Line Diagram for NLDB-7510 | A | Submitted | Rejected | #VALUE! |  | 2018-10-11 | 346 | #N/A | Submitted
349 | DCI | Electrical | GCS-ELSD0012 | Electrical Single Line Diagram for NLDB-7515 | A | Submitted | Rejected | #VALUE! |  | 2018-10-11 | 347 | #N/A | Submitted
350 | DCI | Electrical | GCS-ELSD0013 | Electrical Single Line Diagram for NLDB-8515 | A | Submitted | Rejected | #VALUE! |  | 2018-10-11 | 348 | #N/A | Submitted
351 | DCI | Electrical | GCS-ELSD0014 | Electrical Single Line Diagram for ELDB-7001 | A | Submitted | Rejected | #VALUE! |  | 2018-10-12 | 349 | #N/A | Submitted
352 | DCI | Electrical | GCS-ELSD0015 | Electrical Single Line Diagram for ELDB-7510 | A | Submitted | Rejected | #VALUE! |  | 2018-10-12 | 350 | #N/A | Submitted
353 | DCI | Electrical | GCS-ELSD0016 | Electrical Single Line Diagram for ELDB-7515 | A | Submitted | Rejected | #VALUE! |  | 2018-10-12 | 351 | #N/A | Submitted
354 | DCI | Electrical | GCS-ELSD0017 | Electrical Single Line Diagram for ELDB-8515 | A | Submitted | Rejected | #VALUE! |  | 2018-10-12 | 352 | #N/A | Submitted
355 | DCI | Electrical | GCS-ELSH0001 | Electrical PCC/MCC Feeder Control Schematic Diagram | A | 1 | COMPLETE | #VALUE! |  | 2018-02-09 | 353 | #N/A | Code-1
356 | DCI | Instrumentation & Telecom | P4007-IN-DB-001 | Instrument Design Basis update | A | 1 | COMPLETE | #VALUE! |  | 2017-12-01 | 354 | #N/A | Code-1
357 | DCI | Instrumentation & Telecom | P4007-IN-DS-001 | Instrument Datasheet- Control Valve | A | 2 | COMPLETE | #VALUE! |  | 2018-02-07 | 355 | #N/A | Code-2
358 | DCI | Instrumentation & Telecom | P4007-IN-DS-002 | Instrument Datasheet-Pressure Safety Valve | A | 1 | COMPLETE | #VALUE! |  | 2018-02-14 | 356 | #N/A | Code-1
359 | DCI | Instrumentation & Telecom | P4007-IN-DS-003 | Instrument Datasheet-Shutdown valve | A | 2 | COMPLETE | #VALUE! |  | 2018-02-21 | 357 | #N/A | Code-2
360 | DCI | Instrumentation & Telecom | P4007-IN-DS-004 | Instrument Datasheet-Ultrasonic Flow Meter | A | 2 | COMPLETE | #VALUE! |  | 2018-03-15 | 358 | #N/A | Code-2
361 | DCI | Instrumentation & Telecom | P4007-IN-DS-005 | Instrument Datasheet- Pressure Regulator Valve | A | 2 | COMPLETE | #VALUE! |  | 2018-02-09 | 359 | #N/A | Code-2
362 | DCI | Instrumentation & Telecom | P4007-IN-DS-008 | Instrument Datasheet-Electro Magnetic Flow Meter | A | 2 | COMPLETE | #VALUE! |  | 2018-03-05 | 360 | #N/A | Code-2
363 | DCI | Instrumentation & Telecom | P4007-IN-DS-011 | Instrument Datasheet-Fire and Gas Detectors | A | 2 | COMPLETE | #VALUE! |  | 2018-03-28 | 361 | #N/A | Code-2
364 | DCI | Instrumentation & Telecom | P4007-IN-DS-012 | Instrument Datasheet- Radar Type Level Transmitter | A | 2 | COMPLETE | #VALUE! |  | 2018-03-16 | 362 | #N/A | Code-2
365 | DCI | Instrumentation & Telecom | P4007-IN-DS-013 | Instrument Datasheet- Temperature Transmitter | A | 2 | COMPLETE | #VALUE! |  | 2018-03-23 | 363 | #N/A | Code-2
366 | DCI | Instrumentation & Telecom | P4007-IN-DS-014 | Instrument Datasheet- DP Type Pressure/Flow/Level Transmitter | A | 2 | COMPLETE | #VALUE! |  | 2018-02-23 | 364 | #N/A | Code-2
367 | DCI | Instrumentation & Telecom | P4007-IN-DS-016 | Instrument Datasheet- Pressure/Temperature Gauge | A | 2 | COMPLETE | #VALUE! |  | 2018-02-27 | 365 | #N/A | Code-2
368 | DCI | Instrumentation & Telecom | P4007-IN-DS-017 | Instrument Datasheet- Orifice/Restriction Orifice | A | 2 | COMPLETE | #VALUE! |  | 2018-02-21 | 366 | #N/A | Code-2
369 | DCI | Instrumentation & Telecom | P4007-IN-DS-018 | Instrument Datasheet- Level Gauge | A | 2 | COMPLETE | #VALUE! |  | 2018-03-16 | 367 | #N/A | Code-2
370 | DCI | Instrumentation & Telecom | P4007-IN-DS-020 | Instrument Cable datasheet | A | Submitted | Rejected | #VALUE! |  | 2018-10-10 | 368 | #N/A | Submitted
371 | DCI | Instrumentation & Telecom | P4007-IN-DS-021 | Instrument Datasheet- Turbine Flowmeter | A | 2 | COMPLETE | #VALUE! |  | 2018-06-27 | 369 | #N/A | Code-2
372 | DCI | Instrumentation & Telecom | P4007-IN-DS-022 | Instrument Datasheet - Float Type Level Transmitter | A | 2 | COMPLETE | #VALUE! |  | 2018-06-27 | 370 | #N/A | Code-2
373 | DCI | Instrumentation & Telecom | P4007-IN-IN-001 | Instrument Index DCS & ESD | I | 2 | COMPLETE | #VALUE! |  | 2018-01-18 | 371 | #N/A | Code-2
374 | DCI | Instrumentation & Telecom | P4007-IN-IO-001 | I/O List DCS & ESD | I | 2 | COMPLETE | #VALUE! |  | 2018-01-24 | 372 | #N/A | Code-2
375 | DCI | Instrumentation & Telecom | P4007-IN-PY-001 | Fire & Gas Detection Philosophy | A | 2 | COMPLETE | #VALUE! |  | 2018-01-04 | 373 | #N/A | Code-2
376 | DCI | Instrumentation & Telecom | P4007-IN-RP-001 | SIL Scope of work | A | 1 | COMPLETE | #VALUE! |  | 2018-10-12 | 374 | #N/A | Code-1
377 | DCI | Instrumentation & Telecom | P4007-IN-SC-001 | Instrument Cable Schedule DCS | A | Submitted | Rejected | #VALUE! |  | 2018-09-28 | 375 | #N/A | Submitted
378 | DCI | Instrumentation & Telecom | P4007-IN-SC-002 | Instrument Cable Schedule ESD | A | Submitted | Rejected | #VALUE! |  | 2018-09-28 | 376 | #N/A | Submitted
379 | DCI | Instrumentation & Telecom | P4007-IN-SC-003 | Instrument Cable Schedule FGS | A | Submitted | Rejected | #VALUE! |  | 2018-09-28 | 377 | #N/A | Submitted
380 | DCI | Instrumentation & Telecom | P4007-IN-SC-004 | Instrument JB Schedule DCS | A | 2 | COMPLETE | #VALUE! |  | 2018-10-03 | 378 | #N/A | Code-2
381 | DCI | Instrumentation & Telecom | P4007-IN-SC-005 | Instrument JB Schedule ESD | A | 2 | COMPLETE | #VALUE! |  | 2018-10-03 | 379 | #N/A | Code-2
382 | DCI | Instrumentation & Telecom | P4007-IN-SC-006 | Instrument JB Schedule FGS | A | 2 | COMPLETE | #VALUE! |  | 2018-10-03 | 380 | #N/A | Code-2
383 | DCI | Instrumentation & Telecom | P4007-TE-DS-001 | CCTV Datasheet | A | Deleted | Rejected | #VALUE! |  | 2018-09-25 | 381 | #N/A | #N/A
384 | DCI | Instrumentation & Telecom | P4007-TE-SC-001 | Telecom Cable Schedule | I |  | Rejected | #VALUE! |  | 2018-10-16 | 382 | #N/A | NS
385 | DCI | Instrumentation & Telecom | GCS-INBD0001 | Cable Block Diagram DCS | I | 2 | COMPLETE | #VALUE! |  | 2018-02-08 | 383 | #N/A | Code-2
386 | DCI | Instrumentation & Telecom | GCS-INBD0002 | Cable Block Diagram ESD | I | 2 | COMPLETE | #VALUE! |  | 2018-02-13 | 384 | #N/A | Code-2
387 | DCI | Instrumentation & Telecom | GCS-INBD0003 | Cable Block Diagram FGS | I | 2 | COMPLETE | #VALUE! |  | 2018-02-16 | 385 | #N/A | Code-2
388 | DCI | Instrumentation & Telecom | GCS-INCE0001 | F&G Cause & Effect Diagram | A | Submitted | Rejected | #VALUE! |  | 2018-09-26 | 386 | #N/A | Submitted
389 | DCI | Instrumentation & Telecom | GCS-INHD0001 | Instrument Hook Up Diagrams | I | 2 | COMPLETE | #VALUE! |  | 2018-02-21 | 387 | #N/A | Code-2
390 | DCI | Instrumentation & Telecom | GCS-INIC0001 | Interconnection Diagram | I | Deleted | Rejected | #VALUE! |  | 2018-11-02 | 388 | #N/A | #N/A
391 | DCI | Instrumentation & Telecom | GCS-INID0001 | Installation drawing DCS/ESD | I | 2 | COMPLETE | #VALUE! |  | 2018-10-10 | 389 | #N/A | Code-2
392 | DCI | Instrumentation & Telecom | GCS-INID0002 | Installation drawing FGS | I | 2 | COMPLETE | #VALUE! |  | 2018-10-10 | 390 | #N/A | Code-2
393 | DCI | Instrumentation & Telecom | GCS-INLD0001 | Loop Wiring Diagram DCS | I | Deleted | Rejected | #VALUE! |  | 2018-11-08 | 391 | #N/A | #N/A
394 | DCI | Instrumentation & Telecom | GCS-INLD0002 | Loop Wiring Diagram ESD | I | Deleted | Rejected | #VALUE! |  | 2018-11-08 | 392 | #N/A | #N/A
395 | DCI | Instrumentation & Telecom | GCS-INLD0003 | Loop Wiring Diagram FGS | I | Deleted | Rejected | #VALUE! |  | 2018-11-08 | 393 | #N/A | #N/A
396 | DCI | Instrumentation & Telecom | GCS-INLY0001 | DCS/ESD Instrument Location Layout | A | 2 | COMPLETE | #VALUE! |  | 2018-10-19 | 394 | #N/A | Code-2
397 | DCI | Instrumentation & Telecom | GCS-INLY0002 | Instrument JB & Cable Tray Layout - DCS/ESD | A | Submitted | Rejected | #VALUE! |  | 2018-10-17 | 395 | #N/A | Submitted
398 | DCI | Instrumentation & Telecom | GCS-INLY0003 | Instrument JB & Cable Tray Layout - F&G | A | Deleted | Rejected | #VALUE! |  | 2018-10-16 | 396 | #N/A | #N/A
399 | DCI | Instrumentation & Telecom | GCS-INLY0004 | Control Room Layout | A | 2 | COMPLETE | #VALUE! |  | 2018-01-30 | 397 | #N/A | Code-2
400 | DCI | Instrumentation & Telecom | GCS-INLY0005 | Fire & Gas Detection Field Layout | A | 1 | COMPLETE | #VALUE! |  | 2018-01-30 | 398 | #N/A | Code-1
401 | DCI | Instrumentation & Telecom | GCS-INLY0006 | Fire & Gas Detection Office Building & Control room layout | A | 2 | COMPLETE | #VALUE! |  | 2018-10-05 | 399 | #N/A | Code-2
402 | DCI | Instrumentation & Telecom | GCS-INLY0007 | Fire & Gas Detection Electrical Substation Layout | A | 1 | COMPLETE | #VALUE! |  | 2018-09-27 | 400 | #N/A | Code-1
403 | DCI | Instrumentation & Telecom | GCS-INLY0008 | Fire & Gas Detection Maintenance Room Layout | A | 1 | COMPLETE | #VALUE! |  | 2018-09-27 | 401 | #N/A | Code-1
404 | DCI | Instrumentation & Telecom | GCS-INLY0009 | Fire & Gas Detection Security Room Layout | A | 1 | COMPLETE | #VALUE! |  | 2018-09-27 | 402 | #N/A | Code-1
405 | DCI | Instrumentation & Telecom | GCS-INMI0001 | Electrical interface diagram | I |  | Rejected | #VALUE! |  | 2018-11-03 | 403 | #N/A | NS
406 | DCI | Instrumentation & Telecom | GCS-INSA0001 | System Architecture | A | 1 | COMPLETE | #VALUE! |  | 2018-01-10 | 404 | #N/A | Code-1
407 | DCI | Instrumentation & Telecom | GCS-INSA0002 | CCTV Architecture Diagram | A | Deleted | Rejected | #VALUE! |  | 2018-10-03 | 405 | #N/A | #N/A
408 | DCI | Instrumentation & Telecom | GCS-INSA0003 | EPABX Architecture Diagram | A | Deleted | Rejected | #VALUE! |  | 2018-10-04 | 406 | #N/A | #N/A
409 | DCI | Instrumentation & Telecom | GCS-INWD0001 | Instrument JB Wiring DCS | I | 2 | COMPLETE | #VALUE! |  | 2018-04-06 | 407 | #N/A | Code-2
410 | DCI | Instrumentation & Telecom | GCS-INWD0002 | Instrument JB Wiring ESD | I | 2 | COMPLETE | #VALUE! |  | 2018-04-13 | 408 | #N/A | Code-2
411 | DCI | Instrumentation & Telecom | GCS-INWD0003 | Instrument JB Wiring FGS | I | 2 | COMPLETE | #VALUE! |  | 2018-04-20 | 409 | #N/A | Code-2
412 | DCI | Instrumentation & Telecom | GCS-INWD0004 | Marshalling wiring DCS | I | Submitted | Rejected | #VALUE! |  | 2018-11-06 | 410 | #N/A | Submitted
413 | DCI | Instrumentation & Telecom | GCS-INWD0005 | Marshalling wiring ESD | I | Submitted | Rejected | #VALUE! |  | 2018-11-06 | 411 | #N/A | Submitted
414 | DCI | Instrumentation & Telecom | GCS-INWD0006 | Marshalling wiring FGS | I | Submitted | Rejected | #VALUE! |  | 2018-11-06 | 412 | #N/A | Submitted
415 | DCI | Instrumentation & Telecom | GCS-TEBD0001 | Telecom Cable Block Diagram | A |  | Rejected | #VALUE! |  | 2018-09-27 | 413 | #N/A | NS
416 | DCI | Instrumentation & Telecom | GCS-TELY0001 | Telecom Location Layout | I |  | Rejected | #VALUE! |  | 2018-09-26 | 414 | #N/A | NS
417 | DCI | Instrumentation & Telecom | GCS-TEWD0001 | Telecom Wiring | I | Deleted | Rejected | #VALUE! |  | 2018-11-09 | 415 | #N/A | #N/A
418 | DCI | Safety | GCS-SALY0001 | FIRE FIGHTING AND SAFETY EQUIPMENT FIELD LAYOUT | A | 1 | COMPLETE | #VALUE! |  | 2018-02-14 | 416 | #N/A | Code-1
419 | DCI | Safety | GCS-SALY0002 | Safety Equipment & Safety Signs Building Layout | A | 1 | COMPLETE | #VALUE! |  | 2018-09-27 | 417 | #N/A | Code-1
420 | DCI | Safety | GCS-SALY0003 | Firewater Network Layout | A | 1 | COMPLETE | #VALUE! |  | 2018-02-02 | 418 | #N/A | Code-1
421 | DCI | Safety | GCS-SALY0004 | Fireproofing Layout | A | 1 | COMPLETE | #VALUE! |  | 2018-01-23 | 419 | #N/A | Code-1
422 | DCI | Safety | GCS-SALY0005 | ESCAPE ROUTE & SAFETY SIGNS LAYOUT (FIELD & BUILDING) | A | 1 | COMPLETE | #VALUE! |  | 2018-02-23 | 420 | #N/A | Code-1
423 | DCI | Safety | GCS-SALY0006 | Hazardous Area Classification Layout | A | 2 | COMPLETE | #VALUE! |  | 2018-01-25 | 421 | #N/A | Code-2
424 | DCI | Safety | GCS-SALY0007 | Fire fighting & Safety Equipment Electrical Substation Layout | A | 1 | COMPLETE | #VALUE! | #VALUE! | 2018-06-20 | 422 | #N/A | Code-1
425 | DCI | Safety | GCS-SALY0008 | Fire fighting & Safety Equipment Maintenance Room Layout | A | 1 | COMPLETE | #VALUE! | #VALUE! | 2018-06-22 | 423 | #N/A | Code-1
426 | DCI | Safety | GCS-SALY0009 | Fire fighting & Safety Equipment Security Room Layout | A | 1 | COMPLETE | #VALUE! | #VALUE! | 2018-06-22 | 424 | #N/A | Code-1
427 | DCI | Safety | GCS-SALY0010 | Escape Route & Safety Signs Office Building & Control Room Layout | A | 1 | COMPLETE | #VALUE! |  | 2018-09-27 | 425 | #N/A | Code-1
428 | DCI | Safety | GCS-SALY0011 | Escape Route & Safety Signs Electrical Substation Layout | A | 1 | COMPLETE | #VALUE! | #VALUE! | 2018-06-27 | 426 | #N/A | Code-1
429 | DCI | Safety | GCS-SALY0012 | Escape Route & Safety Signs Maintenance Room Layout | A | 1 | COMPLETE | #VALUE! | #VALUE! | 2018-06-29 | 427 | #N/A | Code-1
430 | DCI | Safety | GCS-SALY0013 | Escape Route & Safety Signs Security Room Layout | A | 1 | COMPLETE | #VALUE! | #VALUE! | 2018-06-29 | 428 | #N/A | Code-1
431 | DCI | Safety | GCS-SAPD0001 | Firewater Tank P&ID | A | 1 | COMPLETE | #VALUE! |  | 2018-01-18 | 429 | #N/A | Code-1
432 | DCI | Safety | GCS-SAPD0002 | Firewater Pumping Station P&ID | A | 1 | COMPLETE | #VALUE! |  | 2018-01-19 | 430 | #N/A | Code-1
433 | DCI | Safety | GCS-SAPD0003 | Firewater Network P&ID | A | 1 | COMPLETE | #VALUE! |  | 2018-02-02 | 431 | #N/A | Code-1
434 | DCI | Safety | GCS-SAPD0004 | Firewater Typical Installation Detail P&ID | A | 1 | COMPLETE | #VALUE! | #VALUE! | 2018-02-09 | 432 | #N/A | Code-1
435 | DCI | Safety | GCS-SAPD0005 | Firewater Spray nozzle Typical Arrangement P&ID | A | 1 | COMPLETE | #VALUE! | #VALUE! | 2018-02-16 | 433 | #N/A | Code-1
436 | DCI | Safety | GCS-SAPF0001 | Firewater System PFD | A | 1 | COMPLETE | #VALUE! |  | 2018-01-04 | 434 | #N/A | Code-1
437 | DCI | Safety | P4007-SA-DB-001 | Loss Prevention Design basis | A | 1 | COMPLETE | #VALUE! |  | 2017-12-20 | 435 | #N/A | Code-1
438 | DCI | Safety | P4007-SA-DS-001 | Fireproofing - List of Potential Sources of Fire | A | 2 | COMPLETE | #VALUE! |  | 2018-01-12 | 436 | #N/A | Code-2
439 | DCI | Safety | P4007-SA-DS-002 | Hazardous Area Classification Schedule | A | 2 | COMPLETE | #VALUE! |  | 2018-01-12 | 437 | #N/A | Code-2
440 | DCI | Safety | P4007-SA-PY-001 | Active Fire Protection Philosophy | A | 1 | COMPLETE | #VALUE! |  | 2018-01-06 | 438 | #N/A | Code-1
441 | DCI | Safety | P4007-SA-RP-002 | Firewater Demand Calculation Report | A | 1 | COMPLETE | #VALUE! |  | 2018-02-15 | 439 | #N/A | Code-1
442 | DCI | Safety | P4007-SA-RP-003 | Hazop Study Report | A | 1 | COMPLETE | #VALUE! |  | 2018-02-19 | 440 | #N/A | Code-1
443 | DCI | Safety | P4007-SA-RP-004 | QRA Study Report | A | 1 | COMPLETE | #VALUE! |  | 2018-02-20 | 441 | #N/A | Code-1
444 | DCI | Safety | P4007-SA-RP-005 | EERA Study Report | A | 1 | COMPLETE | #VALUE! |  | 2018-06-29 | 442 | #N/A | Code-1
445 | DCI | Safety | P4007-SA-RP-006 | Fire Water Spray system Hydraulic Calculation Report | A | 3 | Rejected | #VALUE! |  | 2018-10-05 | 443 | #N/A | Code-3
446 | DCI | Safety | P4007-SA-SP-001 | Active Fire Protection Specifications | A | 2 | COMPLETE | #VALUE! |  | 2018-03-02 | 444 | #N/A | Code-2
447 | DCI | Safety | P4007-SA-SP-002 | Safety Equipment & Safety Sign Specifications | A | 1 | COMPLETE | #VALUE! |  | 2018-03-09 | 445 | #N/A | Code-1
448 | DCI | Safety | P4007-SA-SP-003 | Clean Agent System Specifications | A | 1 | COMPLETE | #VALUE! |  | 2018-03-16 | 446 | #N/A | Code-1
449 | MCI | Mechanical | P4007-ME-PR-001 | Purchase Requisition- Pressure Vessels (LP / MP / HP Gas KOD, Filter Coalescer & Mist Extractor) | A | 1 | COMPLETE | #VALUE! |  | 2018-01-09 | 447 | Code-1 | #N/A
450 | MCI | Mechanical | P4007-ME-PR-002 | Purchase Requisition-HP / LP Gas Compressor Package | A | 2 | COMPLETE | #VALUE! |  | 2018-01-04 | 448 | Code-2 | #N/A
451 | MCI | Mechanical | P4007-ME-PR-003 | Purchase Requisition-Dehydration Package | A | 2 | COMPLETE | #VALUE! |  | 2018-01-03 | 449 | Code-2 | #N/A
452 | MCI | Mechanical | P4007-ME-PR-004 | Purchase Requisition-Fuel Gas System | A | 1 | COMPLETE | #VALUE! | #VALUE! | 2018-01-17 | 450 | Code-1 | #N/A
453 | MCI | Mechanical | P4007-ME-PR-005 | Purchase Requisition-Flare KOD | A | Submitted | Rejected | #VALUE! |  | 2018-10-12 | 451 | Submitted | #N/A
454 | MCI | Mechanical | P4007-ME-PR-006 | Purchase Requisition -Flare KO Pumps | A | 3 | Rejected | #VALUE! | #VALUE! | 2018-01-30 | 452 | Code-3 | #N/A
455 | MCI | Mechanical | P4007-ME-PR-008 | Purchase Requisition-ETP System | A | 3 | Rejected | #VALUE! | #VALUE! | 2018-01-16 | 453 | Code-3 | #N/A
456 | MCI | Mechanical | P4007-ME-PR-009 | Purchase Requisition-Service Water System | A | Submitted | Rejected | #VALUE! |  | 2018-09-28 | 454 | Submitted | #N/A
457 | MCI | Mechanical | P4007-ME-PR-010 | Purchase Requisition-Potable Water System | A | 2 | COMPLETE | #VALUE! |  | 2018-09-28 | 455 | Code-2 | #N/A
458 | MCI | Mechanical | P4007-ME-PR-011 | Purchase Requisition-Methanol Dosing Package | A | 1 | COMPLETE | #VALUE! |  | 2018-01-22 | 456 | Code-1 | #N/A
459 | MCI | Mechanical | P4007-ME-PR-012 | Purchase Requisition-Fire Water System | A | 2 | COMPLETE | #VALUE! |  | 2018-03-06 | 457 | Code-2 | #N/A
460 | MCI | Mechanical | P4007-ME-PR-013 | Purchase Requisition-Oily Water system | A | Deleted | Rejected | #VALUE! |  | 2018-09-27 | 458 | #N/A | #N/A
461 | MCI | Mechanical | P4007-ME-PR-016 | Purchase Requisition-Bore Well Pump | A | 1 | COMPLETE | #VALUE! | #VALUE! | 2018-02-21 | 459 | Code-1 | #N/A
462 | MCI | Mechanical | P4007-ME-PR-018 | Purchase Requisition-Effluent Water Storage Tank | A | 1 | COMPLETE | #VALUE! | #VALUE! | 2018-02-23 | 460 | Code-1 | #N/A
463 | MCI | Mechanical | P4007-ME-PR-019 | Purchase Requisition - Instrument Air Package | A | Submitted | Rejected | #VALUE! |  | 2018-10-01 | 461 | Submitted | #N/A
464 | MCI | Mechanical | P4007-ME-PR-020 | Purchase Requisition-Gas Engine Power Generator System | A | 2 | COMPLETE | #VALUE! |  | 2018-01-11 | 462 | Code-2 | #N/A
465 | MCI | Mechanical | P4007-ME-PR-021 | Purchase Requisition-Emergency Diesel Generator System | A | 3 | Rejected | #VALUE! | #VALUE! | 2018-01-17 | 463 | Submitted | #N/A
466 | MCI | Mechanical | P4007-ME-PR-022 | Purchase Requisition- HOT Crane -(Maintenance & Compressor Building) | A | Submitted | Rejected | #VALUE! |  | 2018-09-28 | 464 | Submitted | #N/A
467 | MCI | Mechanical | P4007-ME-PR-023 | Purchase Requisition - HVAC | A | 1 | COMPLETE | #VALUE! |  | 2018-09-27 | 465 | Code-1 | #N/A
468 | MCI | Mechanical | P4007-ME-PR-024 | Purchase Requisition - Chain Pulley Block | A | Submitted | Rejected | #VALUE! |  | 2018-09-28 | 466 | Submitted | #N/A
469 | MCI | Mechanical | P4007-ME-PR-025 | Purchase Requisition - Inert Gas Generation Pacakge | A | 1 | COMPLETE | #VALUE! | #VALUE! | 2018-06-30 | 467 | Code-1 | #N/A
470 | MCI | Piping | P4007-PI-MT-001 | Piping Bulk MTO | I | 1 | COMPLETE | #VALUE! |  | 2018-10-09 | 468 | Submitted | #N/A
471 | MCI | Piping | P4007-PI-MT-002 | Piping Support MTO | I |  | Rejected | #VALUE! |  | 2018-10-11 | 469 | NS | #N/A
472 | MCI | Piping | P4007-PI-MT-003 | Valve MTO | I | 2 | COMPLETE | #VALUE! |  | 2018-07-11 | 470 | Code-2 | #N/A
473 | MCI | Piping | P4007-PI-MT-004 | Piping Painting MTO | I | Submitted | Rejected | #VALUE! |  | 2018-10-12 | 471 | Submitted | #N/A
474 | MCI | Piping | P4007-PI-MT-005 | Piping Insulation MTO | I |  | Rejected | #VALUE! |  | 2018-10-12 | 472 | NS | #N/A
475 | MCI | Piping | P4007-PI-MT-006 | MTO - Piping Special Items | A | 2 | COMPLETE | #VALUE! |  | 2018-10-05 | 473 | Code-2 | #N/A
476 | MCI | Civil | P4007-CV-MT-001 | BOQ FOR CIVIL WORKS/MTO FOR STRUCTURAL WORKS | I | 2 | COMPLETE | #VALUE! |  | 2018-05-12 | 474 | Code-2 | #N/A
477 | MCI | Electrical | P4007-EL-MT-001 | Electrical Bulk MTO - Cables, Trays, Earthing materials, light fixtures, Junction Boxes, Cable Glands & Other miscellaneous materials | I | Submitted | Rejected | #VALUE! |  | 2018-09-28 | 475 | Submitted | #N/A
478 | MCI | Electrical | P4007-EL-PR-001 | Purchase Requisition for PCC, MCC & PMS panel | A | 1 | COMPLETE | #VALUE! |  | 2018-02-16 | 476 | Code-1 | #N/A
479 | MCI | Electrical | P4007-EL-PR-003 | Purchase Requisition for AC UPS & DB | A | 1 | COMPLETE | #VALUE! |  | 2018-03-09 | 477 | Code-1 | #N/A
480 | MCI | Electrical | P4007-EL-PR-005 | Purchase Requisition for Lighting transformer | A | 1 | COMPLETE | #VALUE! |  | 2018-03-30 | 478 | Code-1 | #N/A
481 | MCI | Electrical | P4007-EL-PR-006 | Purchase Requisition for PDB & Lighting DB's | A | Submitted | Rejected | #VALUE! |  | 2018-09-28 | 479 | Submitted | #N/A
482 | MCI | Electrical | P4007-EL-PR-007 | Purchase Requisition for Electrical Power and control Cables | A | Submitted | Rejected | #VALUE! |  | 2018-09-27 | 480 | Submitted | #N/A
483 | MCI | Electrical | P4007-EL-PR-008 | Purchase Requisition for Lighting Fixtures, Lighting Poles & High mast | A | 1 | COMPLETE | #VALUE! |  | 2018-10-25 | 481 | Code-1 | #N/A
484 | MCI | Instrumentation & Telecom | P4007-IN-MT-001 | Instrument Bulk MTO | I | Submitted | Rejected | #VALUE! |  | 2018-10-16 | 482 | Submitted | #N/A
485 | MCI | Instrumentation & Telecom | P4007-IN-PR-001 | Purchase Requisition- Control Valve | A | 2 | COMPLETE | #VALUE! |  | 2018-02-13 | 483 | Code-2 | #N/A
486 | MCI | Instrumentation & Telecom | P4007-IN-PR-002 | Purchase Requisition-Pressure Safety Valve | A | 2 | COMPLETE | #VALUE! |  | 2018-02-19 | 484 | Code-2 | #N/A
487 | MCI | Instrumentation & Telecom | P4007-IN-PR-003 | Purchase Requisition-Shutdown valve | A | 2 | COMPLETE | #VALUE! |  | 2018-02-26 | 485 | Code-2 | #N/A
488 | MCI | Instrumentation & Telecom | P4007-IN-PR-004 | Purchase Requisition-Ultrasonic Flow Meter | A | 2 | COMPLETE | #VALUE! |  | 2018-03-20 | 486 | Code-2 | #N/A
489 | MCI | Instrumentation & Telecom | P4007-IN-PR-005 | Purchase Requisition- Pressure Regulator Valve | A | 2 | COMPLETE | #VALUE! |  | 2018-02-16 | 487 | Code-2 | #N/A
490 | MCI | Instrumentation & Telecom | P4007-IN-PR-007 | Purchase Requisition-Electro Magnetic Flow Meter | A | 2 | COMPLETE | #VALUE! |  | 2018-03-12 | 488 | Code-2 | #N/A
491 | MCI | Instrumentation & Telecom | P4007-IN-PR-010 | Purchase Requisition-Fire and Gas Detectors | A | 2 | COMPLETE | #VALUE! |  | 2018-04-04 | 489 | Code-2 | #N/A
492 | MCI | Instrumentation & Telecom | P4007-IN-PR-012 | Purchase Requisition-DCS | A | 2 | COMPLETE | #VALUE! |  | 2018-03-02 | 490 | Code-2 | #N/A
493 | MCI | Instrumentation & Telecom | P4007-IN-PR-013 | Purchase Requisition-ESD & FGS | A | 2 | COMPLETE | #VALUE! |  | 2018-03-09 | 491 | Code-2 | #N/A
494 | MCI | Instrumentation & Telecom | P4007-IN-PR-014 | Purchase Requisition- Radar Type Level Transmitter | A | 2 | COMPLETE | #VALUE! |  | 2018-03-23 | 492 | Code-2 | #N/A
495 | MCI | Instrumentation & Telecom | P4007-IN-PR-015 | Purchase Requisition- Coriolis Mass Flow meter | A | 2 | COMPLETE | #VALUE! |  | 2018-03-28 | 493 | Code-2 | #N/A
496 | MCI | Instrumentation & Telecom | P4007-IN-PR-016 | Purchase Requisition- Temperature Transmitter | A | 2 | COMPLETE | #VALUE! |  | 2018-03-30 | 494 | Code-2 | #N/A
497 | MCI | Instrumentation & Telecom | P4007-IN-PR-017 | Purchase Requisition- DP Type Pressure/Flow/Level Transmitter | A | 2 | COMPLETE | #VALUE! |  | 2018-03-01 | 495 | Code-2 | #N/A
498 | MCI | Instrumentation & Telecom | P4007-IN-PR-018 | Purchase Requisition- Displacer Type Level Transmitter | A | 2 | COMPLETE | #VALUE! |  | 2018-03-16 | 496 | Code-2 | #N/A
499 | MCI | Instrumentation & Telecom | P4007-IN-PR-019 | Purchase Requisition- Pressure/Temperature Gauge | A | 2 | COMPLETE | #VALUE! |  | 2018-02-27 | 497 | Code-2 | #N/A
500 | MCI | Instrumentation & Telecom | P4007-IN-PR-020 | Purchase Requisition- Orifice/Restriction Orifice | A | 2 | COMPLETE | #VALUE! |  | 2018-02-28 | 498 | Code-2 | #N/A
501 | MCI | Instrumentation & Telecom | P4007-IN-PR-021 | Purchase Requisition- Level Gauge | A | 2 | COMPLETE | #VALUE! |  | 2018-03-23 | 499 | Code-2 | #N/A
502 | MCI | Instrumentation & Telecom | P4007-TE-MT-001 | Telecom MTO | I |  | Rejected | #VALUE! |  | 2018-10-23 | 500 | NS | #N/A
503 | MCI | Instrumentation & Telecom | P4007-TE-PR-001 | Purchase Requisition- CCTV | A | 1 | COMPLETE | #VALUE! |  | 2018-10-03 | 501 | Code-1 | #N/A
504 | MCI | Instrumentation & Telecom | P4007-TE-PR-002 | Purchase Requisition- EPABX | A | 1 | COMPLETE | #VALUE! |  | 2018-10-04 | 502 | Code-1 | #N/A
505 | MCI | Safety | P4007-SA-PR-001 | Purchase Requisitions - Fire Fighting Equipment | A | 1 | COMPLETE | #VALUE! |  | 2018-03-09 | 503 | Code-1 | #N/A
506 | MCI | Safety | P4007-SA-PR-002 | Purchase Requisitions - Safety Equipment & Safety Sign | A | 1 | COMPLETE | #VALUE! |  | 2018-03-16 | 504 | Code-1 | #N/A
507 | MCI | Safety | P4007-SA-PR-003 | Purchase Requisitions - Clean Agent System | A | 1 | COMPLETE | #VALUE! |  | 2018-03-23 | 505 | Code-1 | #N/A
Note: | Highlighted are rejected initially, due to some information
|  | LEGEND | A: Approval category | I: Information Category
|  |  | 1- Approved | 3-Rejected
|  |  | 2- Approved with comments | 4- Retained for information
Formulas:
Remarks = TODAY()-[For N Days]

## Deleted after 16-jan-2019
SN | DCI/MCI | DISCIPLINE | DOCUMENT No. | DOCUMENT NAME | CODE | Current Status Code
132 | DCI | Piping | GCS-PIDD0003 | Pipe Support GADs | K / A | Deleted
138 | DCI | Civil | P4007-PM-RP-003 | Hydrogeological Report | A | Deleted
149 | DCI | Civil | GCS-CVTD0010 | Standard steel Connection Details | I | Deleted
161 | DCI | Civil | GCS-CVLY0014 | Cable Tray & Duct Supports Structural layout and details | I | Deleted
193 | DCI | Civil | GCS-CVDD0032 | Typical Details Of Temporary Barricade | K / A | Deleted
199 | DCI | Civil | GCS-CVDD0039 | Equipment Foundation Details V-1002 | I | Deleted
201 | DCI | Civil | GCS-CVDD0041 | Equipment Foundation Details V-1502 | I | Deleted
216 | DCI | Civil | GCS-CVDD0058 | Equipment Foundation Details A-4502 A/B | I | Deleted
221 | DCI | Civil | GCS-CVDD0063 | Equipment Foundation Details P-5001 A/B | I | Deleted
223 | DCI | Civil | GCS-CVDD0065 | Equipment Foundation Details P-5004 | I | Deleted
236 | DCI | Civil | GCS-CVDD0081 | Foundation details for misc. electrical and instrument panels | I | Deleted
237 | DCI | Civil | GCS-CVDD0082 | Cable Tray & Duct Supports Foundation and details | I | Deleted
239 | DCI | Civil | GCS-CVDD0084 | GA Drawing for Nitrogen Generation & Air System Shed (Layout /plan /Sectional Elevation) | A | Deleted
242 | DCI | Civil | GCS-CVDD0087 | GA Drawing for Glycol Regen. Shed (Layout /plan /Sectional Elevation) | A | Deleted
245 | DCI | Civil | GCS-CVDD0091 | GA & Steel Details for Generator Room Shed (Layout/Plan/Sectional Elevation) | A | Deleted
257 | DCI | Civil | P4007-CV-RP-010 | Foundation Design calculation for Effluent Water Transfer Pumps | K / A | Deleted
260 | DCI | Civil | P4007-CV-RP-014 | Foundation & RCC Design Calculation for Closed Blow Down Condensate Storage Tank | K / A | Deleted
264 | DCI | Civil | P4007-CV-RP-018 | Equipment Foundation Report Details V-1002 | K / A | Deleted
266 | DCI | Civil | P4007-CV-RP-020 | Equipment Foundation Report Details V-1502 | K / A | Deleted
281 | DCI | Civil | P4007-CV-RP-037 | Equipment Foundation Report Details A-4502 A/B | K / A | Deleted
337 | DCI | Electrical | GCS-ELLY0004 | Plant Cable Layout | K / A | Deleted
383 | DCI | Instrumentation & Telecom | P4007-TE-DS-001 | CCTV Datasheet | K / A | Deleted
390 | DCI | Instrumentation & Telecom | GCS-INIC0001 | Interconnection Diagram | I | Deleted
393 | DCI | Instrumentation & Telecom | GCS-INLD0001 | Loop Wiring Diagram DCS | I | Deleted
394 | DCI | Instrumentation & Telecom | GCS-INLD0002 | Loop Wiring Diagram ESD | I | Deleted
395 | DCI | Instrumentation & Telecom | GCS-INLD0003 | Loop Wiring Diagram FGS | I | Deleted
398 | DCI | Instrumentation & Telecom | GCS-INLY0003 | Instrument JB & Cable Tray Layout - F&G | K / A | Deleted
407 | DCI | Instrumentation & Telecom | GCS-INSA0002 | CCTV Architecture Diagram | K / A | Deleted
408 | DCI | Instrumentation & Telecom | GCS-INSA0003 | EPABX Architecture Diagram | K / A | Deleted
417 | DCI | Instrumentation & Telecom | GCS-TEWD0001 | Telecom Wiring | I | Deleted
460 | MCI | Mechanical | P4007-ME-PR-013 | Purchase Requisition-Oily Water system | K / A | Deleted

## Total Doc Deleted with reason
Deleted on approved BS
Approved BS NO
P4007- MAKUM GCS DELETED DCI (REASONS FOR DELETION)
S.NO | DISCIPLINE | DOCUMENT No. | DOCUMENT NAME | REMARKS
Process
1 | Process | GCS-PRPD0019 | P&ID - Vent System | Vent system is not part of project scope
Mechanical
1 | Mechanical | P4007-ME-DS-030 | Mechanical Datasheet- Sewage Water Pit Pump | Not in scope as per updated P&ID and Equipment List
Civil
1 | Civil | GCS-CVLY0009 | Foundation layout for LP Gas Compressor Shed (Foundation / Plinth / Grade Level) | Drawing not yet issued. Details of this drawing are incuded in the following drawings: GCS-CVDD0016 & GCS-CVDD0017. Hence, this drawing is not required.
2 | Civil | GCS-CVLY0011 | Pipe Trench Layout and Details | Not Envisaged
3 | Civil | P4007-CV-RP-012 | Foundation Design calculation for Bore Well Pump | Not reqired as it is a submersible pump
4 | Civil | P4007-CV-RP-022 | Equipment Foundation Report V-6502 | Not in scope as per updated P&ID and Equipment List
5 | Civil | P4007-CV-RP-025 | Equipment Foundation Report Details T-4504
6 | Civil | P4007-CV-RP-045 | Equipment Foundation Report P-5005 A/B
7 | Civil | GCS-CVDD0015 | Structural Steel Detail for Fire Water Pump Shed | Details are include in GA Drawing
8 | Civil | GCS-CVDD0018 | Structural Steel Detail for Gas Lift Compressor Shed | Details are include in GA Drawing
9 | Civil | GCS-CVDD0024 | Foundation Details for Bore Well Pump - P4501 A/B | Not reqired as it is a submersible pump
10 | Civil | GCS-CVDD0034 | Structural Steel Detail for LP Gas Compressor Shed | Details are include in GA Drawing
11 | Civil | GCS-CVDD0043 | Equipment Foundation Details V-6502 | OIL scope
12 | Civil | GCS-CVDD0046 | Equipment Foundation Details T-4504 | Not in scope as per updated P&ID and Equipment List
13 | Civil | GCS-CVDD0066 | Equipment Foundation Details P-5005 A/B
14 | Civil | GCS-CVDD0072 | Neutralization pits GA&RC details | Not Envisaged
15 | Civil | GCS-CVDD0077 | Cable pulling pits GA& details | Not Envisaged
16 | Civil | GCS-CVDD0084 | GA Drawing for Nitrogen Generation & Air System Shed (Layout /plan /Sectional Elevation) | Nitrogen does not need Shed
17 | Civil | GCS-CVDD0088 | Structural Steel Detail for Glycol Regen. Skid Shed | Details are include in GA Drawing
18 | Civil | GCS-CVDD0039 | GA & RCC Details Of Mist Extractor V-1002 | Details are included in GCS-CVDD0038
19 | Civil | GCS-CVDD0041 | GA & RCC Details Of Coalescer Filter V-1502 | Details are included in GCS-CVDD0040
20 | Civil | P4007-CV-RP-018 | Calculation Report for Mist Extractor V-1002 | Details are included in P4007-CV-RP-017
21 | Civil | P4007-CV-RP-020 | Calculation Report for Coalescer Filter V-1502 | Details are included in P4007-CV-RP-019
22 | Civil | P4007-PM-RP-003 | Hydrogeological Report | Document submitted by HAL separately. Not part of RE documentation
23 | Civil | GCS-CVTD0010 | Standard steel Connection Details | Details are included in Pipe rack and shed drawings
24 | Civil | GCS-CVDD0087 | GA Drawing for Glycol Regen. Shed (Layout /plan /Sectional Elevation) | GAD not required, as it is only a skid and not a shed
25 | Civil | GCS-CVDD0091 | GA & Steel Details for Generator Room Shed (Layout/Plan/Sectional Elevation) | Details coverd in Doc no CVDD011 & CVDD012
26 | Civil | GCS-CVLY0014 | Cable Tray & Duct Supports Structural Steel details | Details covered Pipe rack -Structural steel Layout
27 | Civil | GCS-CVDD0081 | Foundation details for misc. electrical and instrument panels | Details covered in GA & Architectural & RCC for Electrical Substation Room
28 | Civil | GCS-CVDD0082 | Cable Tray & Duct Supports Foundation and details | Details covered Pipe rack -Structural steel Layout
29 | Civil | GCS-CVDD0063 | RCC Details of Closed Blow Down Pump P-5001 A/B | Details covered GA & RCC Details Of CBD System
30 | Civil | GCS-CVDD0065 | RCC Details of Oily Water System Oil Pump P-5004 | Details covered GA & RCC Details Of OWS System
31 | Civil | P4007-CV-RP-014 | Calculation Report for Closed Blow Down Vessel & Pump V-5001 & P-5001 A/B | Details covered CBD System - Pit, vessel, Pump Foundation Report
32 | Civil | P4007-CV-RP-037 | Equipment Foundation Report for RO Pacakge & UV Sterilizer A-4502 A/B | Rest on Control room Roof,reflected in Control room report/dwg.
33 | Civil | GCS-CVDD0058 | RCC Details for RO Pacakge & UV Sterilizer A-4502 A/B | Rest on Control room Roof,reflected in Control room report/dwg.
34 | Civil | P4007-CV-RP-010 | Calculation Report for Effluent Water Transfer Pump P5002 A/B | Rest in CBD pit and covered in CV-RP-042
35 | Civil | GCS-CVDD0032 | Typical Details Of Temporary Barricade | This is a reference document submitted to HAL and is not required to be submitted to OIL/EPCC.
Electrical
1 | Electrical | GCS-ELLY0005 | Cable Layout - Substation | Details are included in Electrical Cable Ladder & Trench layout (GCS-ELLY0003)
2 | Electrical | GCS-ELLY0006 | Overall Lighting Layout | All these layouts are merget into a single Lighting Layout - GCS-ELLY0004 (Electrical Lighting Layout), with separate sheets for each area.
3 | Electrical | GCS-ELLY0007 | Lighting Layout - Electrical Substation
4 | Electrical | GCS-ELLY0008 | Lighting Layout - Control Room
5 | Electrical | GCS-ELLY0009 | Plant Lighting Layout
Instrumentation & Telecom
1 | Instrumentation & Telecom | P4007-IN-DS-006 | Instrument Datasheet-Thermal Mass Flow meter | Not required as per updated P&ID
2 | Instrumentation & Telecom | P4007-IN-DS-007 | Instrument Datasheet-Coriolis Mass Flow meter | Not required as per updated P&ID
3 | Instrumentation & Telecom | P4007-IN-DS-009 | Instrument Datasheet- Moisture Analyzer | Part of vendor scope
4 | Instrumentation & Telecom | P4007-IN-DS-010 | Instrument Datasheet- Oily Water Analyzer | Not required as per updated P&ID
5 | Instrumentation & Telecom | P4007-IN-DS-015 | Instrument Datasheet- Displacer Type Level Transmitter | Not required as per updated P&ID
6 | Instrumentation & Telecom | P4007-IN-DS-019 | Instrument datasheet - Fire Alarm Panel | Merged into PR for F&G
7 | Instrumentation & Telecom | P4007-IN-IN-002 | Instrument Index FGS | Instrument Index for DCS, EDS & F&G combined into one document
8 | Instrumentation & Telecom | P4007-IN-IO-002 | I/O List FGS | I/O list for DCS, EDS & F&G combined into one document
9 | Instrumentation & Telecom | GCS-INLD0004 | Fucntional Loop Schematic | Not required for this project
10 | Instrumentation & Telecom | GCS-INLD0001 | Loop Wiring Diagram DCS | Part of System Vendor Document
11 | Instrumentation & Telecom | GCS-INLD0002 | Loop Wiring Diagram ESD | Part of System Vendor Document
12 | Instrumentation & Telecom | GCS-INLD0003 | Loop Wiring Diagram FGS | Part of System Vendor Document
13 | Instrumentation & Telecom | P4007-TE-DS-001 | CCTV Datasheet | Part of CCTV Vendor document
14 | Instrumentation & Telecom | GCS-INIC0001 | Interconnection Diagram | Details will be covered in Marshalling diagram
15 | Instrumentation & Telecom | GCS-TEWD0001 | Telecom Wiring | Part of Telecom Vendor document
16 | Instrumentation & Telecom | GCS-INSA0002 | CCTV Architecture Diagram | Part of CCTV Vendor document
17 | Instrumentation & Telecom | GCS-INSA0003 | EPABX Architecture Diagram | Part of EPBAX Vendor document
18 | Instrumentation & Telecom | GCS-INLY0003 | F&G - Cable Tray Layout | Detailes are covvered in Instrument Cable Tray Layout
Safety
1 | Safety | GCS-SAPD0006 | Clean Agent System Installation P&ID | Part of vendor scope
2 | Safety | P4007-SA-RP-001 | Vent Gas Dispersion Study | Vent system is not part of project scope. Vent P&ID has been deleted
S.NO | DISCIPLINE | DOCUMENT No. | DOCUMENT NAME | REMARKS
Mechanical
1 | Mechanical | P4007-ME-PR-007 | Purchase Requisition-Closed Blown down System | Merger into the following PRs: 1. PR for Centrifugal Pumps : P4007-ME-PR-006 2. PR for Vertical Submersible Pumps: P4007- ME-PR-013
2 | Mechanical | P4007-ME-PR-014 | Purchase Requisition-Condensate Loading Pumps
3 | Mechanical | P4007-ME-PR-015 | Purchase Requisition-Effluent Water Transfer Pumps
4 | Mechanical | P4007-ME-PR-017 | Purchase Requisition-Effluent Water Disposal Pumps
5 | Mechanical | P4007-ME-PR-013 | Purchase Requisition- Vertical Submersible Pumps | Vertical Submersible pumps are not being procured for this project
Electrical
1 | Electrical | P4007-EL-PR-002 | Purchase Requisition for NGR | Merged with PR of GEG
2 | Electrical | P4007-EL-PR-004 | Purchase Requisition for DC Battery Charger & DB | Merged with PR of AC UPS DB
Instrumentation & Telecom
1 | Instrumentation & Telecom | P4007-IN-PR-006 | Purchase Requisition-Thermal Mass Flow meter | Not required as per updated P&ID
2 | Instrumentation & Telecom | P4007-IN-PR-008 | Purchase Requisition- Moisture Analyzer | Part of vendor scope
3 | Instrumentation & Telecom | P4007-IN-PR-009 | Purchase Requisition- Oily Water Analyzer | Not required as per updated P&ID
4 | Instrumentation & Telecom | P4007-IN-PR-011 | Purchase Requisition- Fire Alarm Control Panel | Mergerd with PR for F&G Detectors : P4007-IN-PR-010, since same vendor will provide File Alarm Control Panel as well.
5 | Instrumentation & Telecom | P4007-IN-PR-022 | Purchase Requisition- GDU PLC | Included as part of GDU MR
Safety
1 | Safety | P4007-SA-MT-001 | MTO - Fire Fighting, Safety Equipment & Safety Sign | Quantities are indicated in Safety Layouts